## NC - Register
Number | Link | NC connected to | Year | Month | Status | COUNTRY | NC issuer (opening) | Date of detection | DETECTION PHASE | n° Order | Project Code CM: | Project: | NC category | Accountable | Accountable CONVERT | NC main subject | NC brief summary&root cause | Treatment progress | Date of treatment closure | Containment Action | Direct cost of Treatment | Indirect costs of Treatment [man-h] | Exposure Risk to application costs | CA Responsible | CA Consulted | Root Cause Analysis | Corrective Action
248 |  | / | 2015 | CANC | canc |  | Timidei | 2015-03-01 |  |  |  |  | NCP |  |  |  | dimensioni vite m20 non corrette | [6 empty] | UT/CQ |  |  | reso al fornitore
249 |  | / | 2015 | 10-oct | c |  | Caporaletti | 2015-10-29 |  |  |  |  | NCS |  |  |  | errore di piegatura selle motore | [6 empty] | fornitore |  |  | aumento del controllo interno da parte del fornitore
250 |  | / | 2015 | 10-oct | c |  | Caporaletti | 2015-10-14 |  |  |  |  | NCS |  |  |  | cavo motore non autorizzato | [6 empty] | Fornitore |  |  | richiesta di rispetto condizioni contrattiuali SIR
251 |  | / | 2015 | 10-oct | c |  | Caporaletti | 2015-10-14 |  |  |  |  | NCS |  |  |  | mancata consegna 3° lotto Commessa 11617 | [6 empty] | Acquisti/Produzione |  |  | programmazione migliore tra controllo interno e spedizione
252 |  | / | 2015 | 12-dec | c |  | Monni | 2015-12-11 |  |  |  |  | NCS |  |  |  | difetti delle cravatte giunte nel cantiere Chile (batch 2) con punzone 2 | [6 empty] | Fornitore |  |  | segregazione del prodotto in attesa di esiti analisi, integrazione delle stesse analisi nel PCQ a partire dal lotto successivo
253 |  | / | 2015 | 10-oct | c |  | Rotolossi | 2015-10-24 |  |  |  |  | NCS |  |  |  | Errato posizionamento del PG21 sulla scatola | [6 empty] | Fornitore |  |  | maggior attenzione del personale addetto. Prova sistematica chiusura stagna
254 |  | / | 2016 | 02-feb | c |  | Spadoni | 2016-02-19 |  |  |  |  | NCS |  |  |  | ITU - Press formed R plate codice kt107104: foro minorato e piega mal effettuata; Press formed L plate codice KT107204 idem kt107104 | [6 empty] | Fornitore |  |  | Controllo della difettosità descritta sull’intera fornitura relativa al 4° lotto Brasile
255 |  | / | 2016 | 02-feb | c |  | Monni | 2016-02-29 |  |  |  |  | NCS |  |  |  | Prodotto difettoso di chiavette unificate rilasciato a SIR | [6 empty] | Fornitore |  |  | azione correttiva definita da CHIAVETTE UNIFICATE
256 |  | / | 2016 | 03-mar | c |  | Monni | 2016-03-07 |  |  |  |  | NCS |  |  |  | MEGACELL - Materiale difettoso reclamato in cantiere | [6 empty] | UT/CQ |  |  | eseguita attività in cantiere
257 |  | / | 2016 | 05-may | c |  | Caporaletti | 2016-05-02 |  |  | 11674 |  | NCS |  |  |  | ITU - Incongruenza disegni meccanici KIT
258 |  | / | 2016 | 05-may | c |  | Monni | 2016-05-31 |  |  | 11674 |  | NCS |  |  |  | ITU - Difetto vite M16x165 (cantiere Ituverava) | [6 empty] | Fornitore |  |  | Non fondata. Inoltrata controreplica e in caso restituzione
259 |  | / | 2016 | 05-may | c |  | Monni | 2016-05-31 |  |  | 11674 | [5 empty] | ITU - Difetto dado flangiato M16 - class 8 - Hot dip galvanized (cantiere Ituverava) | [9 empty] | Dopo ns valutazione la NC risulta infondata
260 |  | / | 2016 | 06-june | c |  | Camponeschi | 2016-06-08 |  |  | 11674 |  | NCS |  |  |  | ITU - Fori cravatte occlusi da zinco | [6 empty] | Fornitore |  |  | Non accordata foratura, se non per eccezione
261 |  | / | 2016 | 06-june | c |  | Monni | 2016-06-13 |  |  | 11678-11679-11680-11681-11682 |  | NCS |  |  |  | MONTALTO - Forniture PROFILUMBRA | [6 empty] | Fornitore |  |  | restituzione materiale e sensibilizzazione su ritardo accumulato
262 |  | / | 2016 | 06-june | c |  | Camponeschi | 2016-06-30 |  |  | 11674 |  | NCS |  |  |  | ITU - Difetto dado M8 - class 8 - Hot dip galvanized - DIN 980 | [6 empty] | Fornitore |  |  | Concordata restituzione, eseguita per 600.000 unità (spedizione avvenuta inizio Agosto). Richiesta a Enerray la chiusura definitiva del problema (email del 19 Apr 2017)
263 |  | / | 2016 | 07-july | c |  | Camponeschi | 2016-07-05 |  |  | 11529-11619 |  | NCS |  |  |  | CILE - Accoppiamento cravatta / sella | [6 empty] | Fornitore |  |  | non presente un problema reale. Inoltrato report in ITA/SPA al Cliente Progetti International
264 |  | / | 2016 | 11-nov | c |  | Monni | 2016-11-02 |  |  | 11813 |  | NCS |  |  |  | HZT - Errata realizzazione main beams | [6 empty] | Fornitore |  |  | NC chiusa con la restoration effettuata su FAT 2/3 e verifica della corretta produzione su FAT 3/A
265 |  | / | 2016 | 11-nov | c |  | Monni | 2016-11-02 |  |  | 11813 |  | NCS |  |  |  | HZT - Errata realizzazione head piles | [6 empty] | Fornitore |  |  | Definita azione correttiva e inoltrata a USIMINAS in data 05/12/2016
266 |  | / | 2016 | 11-nov | c |  | Monni | 2016-11-11 |  |  | 11813 |  | NCS |  |  |  | HZT - Errata realizzazione standard components | [6 empty] | Fornitore |  |  | Deve essere inoltrato report al fornitore USIMINAS
267 |  | / | 2016 | 11-nov | c |  | Monni | 2016-11-11 |  |  | 11813 |  | NCS |  |  |  | HZT - Errata realizzazione kit piles | [6 empty] | Fornitore |  |  | Deve essere inoltrato report al fornitore USIMINAS
268 |  | / | 2016 | 11-nov | c |  | Monni | 2016-11-21 |  |  | 11674 |  | NCS |  |  |  | ITU - Difetto dado M10 - class 8 - Hot dip galvanized - DIN 980 | [6 empty] | Fornitore |  |  | Concordata restituzione, in corso di esecuzione per 50.000 unità vite, 50.000 unità dado e 200.000 unità rondella. Richiesta a Enerray la chiusura definitiva del problema (email del 19 Apr 2017)
269 |  | / | 2016 | 11-nov | c |  | Monni | 2016-11-29 |  |  | 11813 |  | NCS |  |  |  | HZT- scarsa adesione rivestimento galvanizzato componenti KIT/STD | [6 empty] | Fornitore |  |  | Definita azione correttiva e inoltrata a USIMINAS in data 05/12/2016
270 |  | / | 2016 | 12-dec | c |  | Monni | 2016-12-06 |  |  | 11813 |  | NCS |  |  |  | HZT- central and middle saddles - errore di piegatura | [6 empty] | Fornitore |  |  | Definita azione correttiva e inoltrata a USIMINAS in data 06/12/2016
271 |  | / | 2017 | 01-jan | c |  | Monni | 2017-01-26 |  |  | 11813 |  | NCS |  |  |  | HZT- problema scarico OMEGA PILES a Tabocas | [6 empty] | Fornitore |  |  | Definita azione correttiva con USI/TECTOR
272 |  | / | 2017 | 02-feb | c |  | Monni | 2017-02-25 |  |  | 11813 |  | NCS |  |  |  | HZT- problema scarico pallets SM (Groupage) a Tabocas | [6 empty] | Fornitore |  |  | Definita azione correttiva con USI/SM
273 |  | / | 2017 | 02-feb | c |  | Monni | 2017-02-25 |  |  | 11813 |  | NCS |  |  |  | HZT- instabilità big bags (PLATES) rilevati a GALVAMINAS (FAT 3-B) | [6 empty] | Fornitore |  |  | Definita azione correttiva con USI/GALVAMINAS
274 |  | / | 2017 | 02-feb | c |  | Monni | 2017-02-25 |  |  | 11813 |  | NCS |  |  |  | HZT- 3 fasci di main beam mancanti all'arrivo a Tabocas (PL 39) | [6 empty] | Fornitore |  |  | Definita azione correttiva con USI/BBOSCH
275 |  | / | 2017 | 03-mar | c |  | Monni | 2017-03-17 |  |  | 11813 |  | NCS |  |  |  | HZT- mancato rispetto delle consistenze previste per FAT 3-D | [6 empty] | Fornitore |  |  | Definita azione correttiva con USI
276 |  | / | 2017 | 03-mar | c |  | Monni | 2017-03-09 |  |  | 11813 |  | NCS |  |  |  | HZT- scarso rivestimento galvanizzato ce mancata palletizzazione componenti Head Piles (FAT 3-C) | [6 empty] | Fornitore |  |  | DA INOLTRARE - Da definire azione correttiva con USI/SCSM
277 |  | / | 2017 | 04-apr | c |  | Monni | 2017-04-04 |  |  | 11898 |  | NCS |  |  |  | ZAMBIA - Difetto dado M8 - class 8 - Hot dip galvanized - DIN 980 | [6 empty] | Fornitore |  |  | La soluzione sul componente va riscontrata in sede di collaudo presso il fonitore
278 |  | / | 2017 | 04-apr | c |  | Monni | 2017-04-11 |  |  | 11813 |  | NCS |  |  |  | HZT- materiale mancante (PL 174 e 192) | [6 empty] | Fornitore |  |  | Definita azione correttiva con USI
279 |  | / | 2017 | 04-apr | c |  | Monni | 2017-04-26 |  |  | 11898 |  | NCS |  |  |  | ZAMBIA - Rilevazione difetti TESTA PALO INTERMEDIA/FINALE durante controllo interno del 20/04/2017 | [6 empty] | Fornitore |  |  | Definito trattamento (accettazione in deroga, sotto condizione) e azione correttiva, da riscontrarsi con visita in sito (settimana 17)
280 |  | / | 2017 | 04-apr | c |  | Monni | 2017-04-27 |  |  | 11931 |  | NCS |  |  |  | SENEGAL - Rilevazione difetti viti di accoppiamento TESTE PALO INTERMEDIA/FINALE - CENTRALI durante controllo interno | [6 empty] | Fornitore |  |  | Definito trattamento (accettazione in deroga, sotto condizione) e azione correttiva, da riscontrarsi con Ufficio Acquisti e Pianificazione/Logistica
281 |  | / | 2017 | 05-may | c |  | Monni | 2017-05-04 |  |  | 11948 |  | NCS |  |  |  | MAGAZZINO - Rilevazione difetto boccola allentata attuatori lineari MATTU0003.11 durante controllo interno | [6 empty] | Fornitore |  |  | Attesa replica SIR per migliorare prototipo Codice CONVERT MATTU0003.11 su indicazione di Ing. Timidei, mail 01/08
282 |  | / | 2017 | 05-may | c |  | Monni | 2017-05-12 |  |  | 11813 |  | NCS |  |  |  | HZT - Pali con lughezza inferiore a quella minima (Artefatos) | [6 empty] | Fornitore |  |  | Sostituzione pali immediata
283 |  | / | 2017 | 06-june | c |  | Monni | 2017-06-13 |  |  | 11813 |  | NCS |  |  |  | HZT - Errate attività di montaggio Enerray su MP 11 (Horizonte) | [6 empty] | Fornitore |  |  | Richiesto piano di rimedio per MP 11 e piani preventivi/summary reports per successive attività FISSATO PIANO DI RIPRISTINO ENTRO 24/8 (email ENERRAY del 18 Aug 2017)
284 |  | / | 2017 | 07-july | c |  | Monni | 2017-07-07 |  |  | 11813 |  | NCS |  |  |  | HZT - Errata fornitura REX di M8 DIN 980 (52.000 pcs circa) | [6 empty] | Fornitore |  |  | Materiale sostituito. Arrivato in cantiere 17 Aug con PL C287 (52k pcs)
285 |  | / | 2017 | 07-july | c |  | Monni | 2017-07-13 |  |  | 11813 |  | NCS |  |  |  | HZT - Main beams partially filled with sand (HZT) | [6 empty] | Fornitore |  |  | Richiesto ad Enerray attenzione nella movimentazione e montaggio del particolare. Ricevuta dettaglio azione in data 21/8
286 |  | / | 2017 | 07-july | c |  | Monni/Dominici | 2017-07-17 |  |  | 11945-11946 |  | NCS |  |  |  | CM 11945 - CM 11946 - Errata esecuzione del cordone di saldatura per il componente sella intermedia (estensione del problema per CM 11898 Zambia) | [6 empty] | Fornitore |  |  | Accettazione in deroga per commesse CM 11945-11946 (Ordine 21544), con approvazione UT/De Cataldo. La CONVERT ITALIA eseguirà alcune verifiche (prove di carico) su dei campioni prelevati presso De Min. Allo stato attuale, in attesa degli esiti di dette prove e della documentazione aggiuntiva da parte del referente tecnico De Min (circa la impossibilità dichiarata di procedere alla esecuzione del cordone 6x6), si conferma la mancata accettabilità di detto componente per commessa CM 11898 (Zambia, OF 21323 rev1). 15/12: Antonio Timidei conferma validità soluzione 8x8 mm e dispone deroga per quanto prodotto da DE MIN, con opportuna disposizione in campo di detti componenti
287 |  | / | 2017 | 07-july | c |  | Monni | 2017-07-17 |  |  | 11813 |  | NCS |  |  |  | HZT - Enerray malpractice adopted for warehousing/moving CONVERT materials at site | [6 empty] | Fornitore |  |  | Richiesto piano di rimedio e inventory check immediato. Quality Control Plan come azione correttiva
288 |  | / | 2017 | 07-july | c |  | Monni | 2017-07-26 |  |  | 11813 |  | NCS |  |  |  | HZT - Enerray wrongly thightening of M8x16 BOLT with M8 DIN 934 NUT (MOD SUPPORT BEAM) | [6 empty] | Fornitore |  |  | Richiesto piano di rimedio e inventory check immediato. Formazione agli operatori quale attenzione ai parametri di serraggio previsti nel Manuale di installazione TRATTAMENTO E AZIONE CORRETTIVA ACCETTABILE INOLTRATA IN DATA 21 AUG 2017 (REVISIONATO MANUALE ASSEMBLAGGIO REV 2) Ramon: survey del 17 Aug 2017 serraggio non positivo
289 |  | / | 2017 | 07-july | c |  | Monni | 2017-07-27 |  |  | 11813 |  | NCS |  |  |  | HZT - Errata fornitura REX di dadi M8 DIN 980 (ulteriori 88.000 pcs). Prudenzialmente, dovuto a test serraggio non andati a buon fine direi di prevedere la disponibilità di una ulteriore quantità di 60.000 dadi M8 DIN 980 e 70.000 M10 DIN 980. Per lo stesso motivo richiesti 70.000pcs M10 DIN980 | [6 empty] | Fornitore |  |  | M8 Materiale in sostituzione. Previsto arrivo in cantiere 17 Aug con PL C289 (130 k pcs) M10 Richiesto chiarimento in data 17 Aug 2017 a Ramon per trovare una soluzione
290 |  | / | 2017 | 07-july | c |  | Monni | 2017-07-29 |  |  | 11813 |  | NCS |  |  |  | HZT - Enerray malpractice adopted for warehousing/moving CONVERT materials at site (Wet SKC) | [6 empty] | Fornitore |  |  | Richiesto piano di rimedio e inventory check immediato. Quality Control Plan come azione correttiva
291 |  | / | 2017 | 08-aug | c |  | Monni | 2017-08-07 |  |  | 11948 |  | NCS |  |  |  | MAGAZZINO - Rilevazione lunghezza eccessiva dei cavi di colore bianco nella calotta degli attuatori lineari MATTU0003.13 | [6 empty] | Fornitore |  |  | Richiesta definizione ed analisi delle cause al fornitore, per successiva attuazione di trattamento ed azione correttiva
292 |  | / | 2017 | 08-aug | c |  | EGP/LS | 2017-08-21 |  |  | 11813 |  | NCS |  |  |  | HZT - Richiesta di formalizzazione subappalto HZT (ENERRAY/AMFER) con 2 NC separate da parte di EGP | [6 empty] | Fornitore |  |  | Fornitra replica con modello contrattiuale OI 65. In attesa di definitiva firma EGP (Pinho) e dei modelli di richiesta effettivamente inoltrati a EGP
293 |  | / | 2017 | 08-aug | c |  | Camponeschi | 2017-08-24 |  |  | 11813 |  | NCS |  |  |  | HZT - Errata esecuzione ramming pile e relativi aggiustamenti in campo (NC 115 attivata da Afaplan) | [6 empty] | Fornitore |  |  | PROPOSTA DEFINIZIONE DI TRATTAMENTO IN DATA 24 AUG 2017 rimozione e identificazione assi interessati alla errata pratica. Riposizionamento a seguito della approvazione della procedura da parte di EGP AZIONE CORRETTIVA ACCETTABILE INOLTRATA IN DATA 24 AUG 2017 Training sui subappaltatori AMFER/GLOBAL, mistery audits e daily reporting to CDB sui risultati raggiunti
294 |  | / | 2017 | 09-sep | c |  | Camponeschi | 2017-09-19 |  |  | 11813 |  | NCS |  |  |  | HZT - Corrugato per il passaggio del cavo dell'attuatore tagliato troppo corto_Enerray | [6 empty] | Fornitore |  |  | Enerray deve lavorare secondo quanto indicato da Convert, controllando continuamente i suoi subappaltatori.
295 |  | / | 2017 | 09-sep | c |  | Camponeschi | 2017-09-19 |  |  | 11813 |  | NCS |  |  |  | HZT - NC 57 attivata da Afaplan riguardo avvallamenti nel campo fotovoltaico | [6 empty] | Fornitore |  |  | out from SoW Convert
296 |  | / | 2017 | 09-sep | c |  | Camponeschi | 2017-09-19 |  |  | 11813 |  | NCS |  |  |  | HZT - NC 146 attivata da Afaplan riguardo all'altezza della SKC troppo bassa rispetto quella prevista da progetto | [6 empty] | Fornitore |  |  | vedi NC 299
297 |  | / | 2017 | 09-sep | c |  | Camponeschi | 2017-09-19 |  |  | 11813 |  | NCS |  |  |  | HZT - NC 125 attivata da Afaplan riguardo un cablaggio non regolare causato dall'altezza della SKC troppo bassa rispetto al progetto (aspetto già evidenziato in NC 146 di Afaplan) | [6 empty] | Fornitore |  |  | vedi NC 299
298 |  | / | 2017 | 09-sep | c |  | Camponeschi | 2017-09-21 |  |  | 11813 |  | NCS |  |  |  | HZT - Montaggio supporti moduli incompleto da parte di Enerray. NC 147 attivata da Afaplan | [6 empty] | Fornitore |  |  | individuazione da parte di Enerray di situazioni di lavoro incompleto per successiva terminazione. Azione correttiva, formazione continua agli operatori e audits senza preavviso.
299 |  | / | 2017 | 09-sep | c |  | Camponeschi | 2017-09-21 |  |  | 11813 |  | NCS |  |  |  | HZT -Montaggio della SKC da parte di Enerray ad una quota inferiore rispetto quella prevista da progetto causando anche stress nei cavi al momento del cablaggio. | [6 empty] | Fornitore |  |  | Enerray deve procedere rimuovendo il terreno non compattato fino a raggiungere la quota di progetto. Per le SKC già montate (trattamento) la rimozione deve essere senza l'utilizzo di macchine al fine di non danneggiare le SKC. Per le nuove SKC da montare, dopo previo controllo della quota, se necessario rimuovere terra non compattata potrà essere fatto con l'ausilio di macchinari.
300 |  | / | 2017 | 09-sep | c |  | Ramon Gomes | 2017-09-16 |  |  | 11813 |  | NCS |  |  |  | HZT - Richiesta RDO giornaliera da parte di EGP indicandolo come Item contrattuale. Nel contratto non c'è evidenza di quanto richiesto, comunque Convert condivide appena possibile RDO a favore di EGP | [6 empty] | EGP |  |  | In attesa da parte di EGP ammissione di mancanza su contratto di tale richiesta e benestare a procedere come attualmente Convert sta facendo.
301 |  | / | 2017 | 09-sep | c |  | Camponeschi | 2017-09-27 |  |  | 11813 |  | NCS |  |  |  | HZT - Mancanza di preservazione sui componenti gia montati da parte di Enerray. Pozzetti in PVC danneggiati | [6 empty] | EGP |  |  | Enerray ha identificato i pozzetti danneggiati e risistemati. Il personale del fornitore è stato formato allo scopo. Fornite evidenze
302 |  | / | 2017 | 10-oct | c |  | Camponeschi | 2017-10-02 |  |  | 11948 |  | NCS |  |  |  | MAGAZZINO - Chiavette intercettate in SIR con doppio difetto. Piattello danneggiato e di spessore non uniforme sulla larghezza. | [6 empty] | Fornitore |  |  | ripresi i componenti in oggetto, sostituiti con altrettanti buoni. Condiviosne di UT di Convert con Chiavette (Caradonna) riguardo il benestare all'utilizzo anche dei componenti con tale difettosità, riscontrati essere in numero di 1091 pz.
303 |  | / | 2017 | 10-oct | c |  | Camponeschi | 2017-10-24 |  |  | 11813 |  | NCS |  |  |  | HZT - errato cablaggio delle SKC da parte di Enerray _ rimuovendo il cavo giallo/verde di connessione tra il connettore n° 10 del segnale motore e la barra di terra | [6 empty] | Fornitore |  |  | Trasmesso allegato tecnico alla quale attenersi. Stabilita formazione ai subappaltatori di Enerray nella giornata di Lun 30-10-17
304 |  | / | 2017 | 10-oct | c |  | Monni | 2017-10-25 |  |  | 11813 |  | NCS |  |  |  | HZT - errato posizionamento del corrugato contenente cavo 7G da parte di Enerray _ il cavo 7G tocca il palo nel raggiungimento del collegamento con attuatore | [6 empty] | Fornitore |  |  | Richiesto un piano di recupero delle errate disposizioni del palo, quando il cavp 7G viene in contatto con il palo stesso. Il piano di rimedio deve essere completato entro 15/11. Stabilita formazione ai subappaltatori di Enerray come fase post trattamento
305 |  | / | 2017 | 11-nov | c |  | Monni | 2017-11-22 |  |  | 11813 |  | NCS |  |  |  | HZT - palo franato/affossato nel terreno | [6 empty] | Fornitore |  |  | TBD
306 |  | / | 2017 | 12-dec | c |  | Camponeschi | 2017-12-15 |  |  | 11980 |  | NCS |  |  |  | SAO PEDRO - errata produzione HEAD CENTRAL PILE (USI/FAFs) | [6 empty] | Fornitore |  |  | Richiesto un piano di recupero per quanto prodotto e azione correttiva per successiva produzione stesso componente
307 |  | / | 2017 | 12-dec | c |  | Morais Jordan | 2017-12-15 |  |  | 11980 |  | NCS |  |  |  | SAO PEDRO - errato serraggio HEAD PILES (USI/Califer) | [6 empty] | Fornitore |  |  | Richiesto un piano di recupero per quanto prodotto/serrato e azione correttiva per successiva produzione stesso componente (uso di avvitatore appropriato)
308 |  | / | 2017 | 12-dec | c |  | Camponeschi | 2017-12-21 |  |  | 11980 |  | NCS |  |  |  | SAO PEDRO - errata produzione cravatte/selle terminali (USI) | [6 empty] | Fornitore |  |  | Richiesto un piano di recupero per quanto prodotto e azione correttiva per successiva modiifca impostazione produzione stesso componente
309 |  | / | 2018 | 02-feb | c |  | Morais Jordan | 2018-02-08 |  |  | 11980 |  | NCS |  |  |  | SAO PEDRO- moraletti non adeguati. Non può essere ritenuta una NC ufficiale in quanto fa parte anche del nostro S.o.W. | [6 empty] | Fornitore |  |  | la tracciamo qui in quanto inoltrata ad USI e presa da loro in carico comunque via mail per ATLAS.
310 |  | / | 2018 | 02-feb | c |  | Morais Jordan | 2018-02-09 |  |  | 11980 |  | NCS |  |  |  | SAO PEDRO-imballo non idoneo delle Main Beam che causa scorrimento delle stesse determinando problemi di sicurezza e danneggiando i componenti (qualità) | [6 empty] | Fornitore |  |  | accordo sulle risoluzione da prendere tra MDC/CDC ed Humberto (USI).
311 |  | / | 2018 | 02-feb | c |  | Morais Jordan | 2018-02-09 |  |  | 11980 |  | NCS |  |  |  | SAO PEDRO-imballo casse di legno di FAFS (supporti A/B/C long plate) non idoneo, causando rottura della cassa e fuoriuscita materiale | [6 empty] | Fornitore |  |  | rinforzo degli angoli delle casse con due barre di legno e degli angolare in legno ad unirle.
312 |  | / | 2018 | 02-feb | c |  | Morais Jordan | 2018-02-19 |  |  | 11980 |  | NCS |  |  |  | SAO PEDRO-imballo non idoneo dei supporti di tipo Beam che causa scorrimento delle stesse determinando problemi di sicurezza e danneggiando i componenti (qualità) | [6 empty] | Fornitore |  |  | aumento di reggette e uso di angolari per impedire la deformazione dei componenti a causa delle reggette visti gli spessori.
313 |  | / | 2018 | 02-feb | c |  | Andrea Monni (on beahalf of Ramon Gomes) | 2018-02-28 |  |  | 11980 |  | NCS |  |  |  | SAO PEDRO-errata manovra di un conducente di camion che stava consegnando in sito c/Convert do Brasil | [6 empty] | Fornitore |  |  | espulsione del conducente (ricusato) Informazione alle ditte coinvolte (tutte) compresa Lesson Learnt (near miss) Rafforzamento controlli area pre-scarico attraverso il personale in sito
314 |  | / | 2018 | 03-mar | c |  | Queiroz Fernando | 2018-03-08 |  |  | 11980 |  | NCS |  |  |  | SAO PEDRO-Conduspar. Bobina danneggiata | [6 empty] | Fornitore |  |  | Conduspar deve sostiuire la bobina danneggiata con una nuova (trattamento). Capire come poter evitare il ripetersi del problema (azione correttiva)
315 |  | / | 2018 | 03-mar | c |  | Queiroz Fernando | 2018-03-14 |  |  | 11980 |  | NCS |  |  |  | SAO PEDRO-Attuatori ammaccati. Vs RNC012 Atlas | [6 empty] | Fornitore |  |  | Gli attuatori ammaccati possono essere determinati anche da trasporti in cantiere del cliente. Chiuso da Atlas sul loro colaborativo system
316 |  | / | 2018 | 03-mar | c |  | Camponeschi | 2018-03-28 |  |  | 11529-11619 |  | NCS |  |  |  | Probelma 1 attuatore Carrera Pinto - sensore IN | [6 empty] | Fornitore |  |  | programmato invio attuatore in SIR per analisi
317 |  | / | 2018 | 04-apr | c |  | Camponeschi | 2018-04-19 |  |  | 12010 |  | NCS |  |  |  | BIOSAR-zincatura dei pali non perfettamente aderita sui bordi. | [6 empty] | Fornitore |  |  | monitoraggio prossime forniture
318 |  | / | 2018 | 06-june | c |  | Camponeschi | 2018-06-01 |  |  | 12010 |  | NCS |  |  |  | BIOSAR - Barre filletate non conformi (REX) | [6 empty] | Fornitore |  |  | Richiesto trattamento ed azione correttiva
319 |  | / | 2018 | 06-june | c |  | Camponeschi | 2018-06-11 |  |  | 11981 |  | NCS |  |  |  | JUAZEIRO - Main beam danneggiate VLI (trasporto treno) | [6 empty] | Fornitore |  |  | Azione di correzione sul sistema di trasporto
320 |  | / | 2018 | 06-june | c |  | Camponeschi | 2018-06-13 |  |  | 12011 |  | NCS |  |  |  | S&W - Ritardo di produzione vs ordine. The Supplier Tubos Argentinos S.A. is doesn’t respecting the Order Contractual Schedule, delaying production times and Cordillera Solar Project Delivery Schedule. | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
321 |  | / | 2018 | 06-june | c |  | Queiroz Fernando | 2018-06-21 |  |  | 11984 |  | NCS |  |  |  | JUAZEIRO - Omega Piles damaged on surface | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
322 |  | / | 2018 | 06-june | c |  | Queiroz Fernando | 2018-06-21 |  |  | 11981 |  | NCS |  |  |  | JUAZEIRO - Wooden Box and bags very well damaged (USIMINAS) | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
323 |  | / | 2018 | 06-june | c |  | Queiroz Fernando | 2018-06-21 |  |  | 11981 |  | NCS |  |  |  | JUAZEIRO - Omega Piles damaged on surface | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
324 |  | / | 2018 | 06-june | c |  | Queiroz Fernando | 2018-06-21 |  |  | 11980 |  | NCS |  |  |  | SAO PEDRO - Sendmizir spacers for Canadian Modules - smaller holes than expected | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
325 |  | / | 2018 | 06-june | c |  | Queiroz Fernando | 2018-06-21 |  |  | 11980 |  | NCS |  |  |  | SAO PEDRO - Head piles with holes of smaller diameter (threaded bars don't pass the holes) - USIMINAS | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
326 |  | / | 2018 | 07-july | c |  | Andrea Monni | 2018-07-09 |  |  | 12041-12042-12043 |  | NCS |  |  |  | ENERRAY _ EGITTO - telo protezione utilizzato per pallets della Bulloneria non adegiuato (BULFER) | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
327 |  | / | 2018 | 07-july | c |  | Monni/Dominici | 2018-07-21 |  |  | 12010 |  | NCS |  |  |  | CM 12010 - Cedimento in campo del componente sella intermedia | [6 empty] | Fornitore |  |  | TO BE DEFINED
328 |  | / | 2018 | 07-july | c |  | Antonio Timidei | 2018-07-23 |  |  | 12010-12011-11980-11981 |  | NCS |  |  |  | REX non compliant bolt_connessa a NC318 | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
329 |  | / | 2018 | 08-aug | c |  | Fernando Queiroz | 2018-08-09 |  |  | 11981 |  | NCS |  |  |  | RNC-010 GrupoEnergia_End Saddle bend angle error | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
330 |  | / | 2018 | 08-aug | c |  | Fernando Queiroz | 2018-08-28 |  |  | 11981 |  | NCS |  |  |  | REX_threaded rod threads damaged | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
331 |  | / | 2018 | 08-aug | c |  | Mandrini | 2018-08-30 |  |  | 11898-11948 |  | NCI |  |  |  | Control unit SKC | [6 empty] | Interna |  |  | Azione di correzione indicata nella NC
332 |  | / | 2018 | 10-oct | c |  | Massimo Mandrini | 2018-10-08 |  |  | 11898 |  | NCS |  |  |  | Non corrispondenza ordine consegna DDT | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
333 |  | / | 2018 | 10-oct | c |  | Camponeschi | 2018-10-11 |  |  | 12040 |  | NCS |  |  |  | Washer M6 not galvanized accordingly to ISO 4042. | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
334 |  | / | 2018 | 11-nov | c |  | Camponeschi | 2018-11-13 |  |  | 11898 |  | NCS |  |  |  | Zambia Aveng-Transvaal_Module Support A-Long Plate_Galvaniz | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
335 |  | / | 2018 | 11-nov | c |  | Rodrigues | 2018-11-20 |  |  | 11981 |  | NCS |  |  |  | JUAZEIRO_REX 1_Convert do Brasil
336 |  | / | 2018 | 11-nov | c |  | Rodrigues | 2018-11-20 |  |  | 11981 |  | NCS |  |  |  | REX_2 Convert do Brasil
337 | link 337 | / | 2019 | 02-feb | c | EMEA | Camponeschi | 2019-02-01 |  |  | 12081 |  | NCC |  | LOGISTIC |  | NCR EGP 26_EUDER_Deformazione cartoni attuatori trasportati |  | 2019-02-22 |  |  |  |  | Fornitore |  |  | Azione di correzione indicata nella NC
338 | link 338 | / | 2019 | 02-feb | c | EMEA | Camponeschi | 2019-02-12 |  |  | 12081 |  | NCC | CSI |  |  | NCR EGP 30_EUDER_Presenza bave main beam consegnate |  | 2019-04-09 |  |  |  |  | Fornitore |  |  | Azione di correzione indicata nella NC
339 | link 339 | / | 2019 | 02-feb | c | EMEA | Camponeschi | 2019-02-12 |  |  | 12081 |  | NCC | CSI |  |  | NCR EGP 32_EUDER_Presenza residui zinco pali consegnati |  | 2019-04-09 |  |  |  |  | Fornitore |  |  | Azione di correzione indicata nella NC
340 | link 340 | / | 2019 | 02-feb | c | LATAM | Camponeschi | 2019-02-14 |  |  | 12155 |  | NCS | DRUETTA |  |  | ULLUM_DRUETTA_Short and Long Omega Pile | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
341 | link 341 | / | 2019 | 02-feb | c | LATAM | Camponeschi | 2019-02-21 |  |  | 12155 |  | NCC | SIDERSA |  | HSE | ULLUM_Elmya_main beam oleose_contaminazione ambiente | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
342 | link 342 | / | 2019 | 03-mar | c | EMEA | Camponeschi | 2019-03-15 |  |  | 12081 |  | NCC | DEMIN |  |  | NCR EGP 53_Euder_ritorno da campo_zincaturaDemin |  | 2019-10-21 |  |  |  |  | Fornitore |  |  | Azione di correzione indicata nella NC
343 | link 343 | / | 2019 | 03-mar | c | EMEA | Camponeschi | 2019-03-15 |  |  | 12081 |  | NCC | I&S |  |  | NCR EGP 53_Euder_ritorno da campo_zincaturaI&S |  | 2019-10-21 |  |  |  |  | Fornitore |  |  | Azione di correzione indicata nella NC
344 | link 344 | / | 2019 | 03-mar | c | EMEA | Camponeschi | 2019-03-18 |  |  | 12081 |  | NCC | CSI |  |  | NCR EGP 53_Euder_ritorno da campo_Pile senza asole |  | 2019-04-09 |  |  |  |  | Fornitore |  |  | Azione di correzione indicata nella NC
345 | link 345 | / | 2019 | 03-mar | c | LATAM | Camponeschi | 2019-03-17 |  |  | 12011 |  | NCS | TUBOS ARGENTINOS |  |  | S&W_main beam Tubos ossidate | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
346 | link 346 | / | 2019 | 03-mar | c | EMEA | Camponeschi | 2019-03-20 |  |  | 12081 |  | NCS | DEMIN |  |  | Euder_Demin_teste palo_spessore zincatura nc |  | n.a. |  |  |  |  | Fornitore |  |  | Azione di correzione indicata nella NC
347 | link 347 | / | 2019 | 03-mar | c | LATAM | Rodrigues | 2019-03-22 |  |  | 12154 |  | NCS | MD LOGISTICA |  |  | MD LOGISTICA_Main beam danneggiata durante trasporto. | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
348 | link 348 | / | 2019 | 03-mar | c | LATAM | Rodrigues | 2019-03-22 |  |  | 12154 |  | NCS | SIDERSA |  |  | CAFAYATE_SIDERSA_Main beam danneggiata durante trasporto | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
349 | link 349 | / | 2019 | 03-mar | c | LATAM | Monni | 2019-03-26 |  |  | 11981 |  | NCS |  | ENGINEERING | STRONG WIND | JUAZEIRO_Strong wind events_15 March 2019 | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
350 | link 350 | / | 2019 | 03-mar | c | LATAM | Sanchez Perez | 2019-03-28 |  |  | 12154 |  | NCS | MD LOGISTICA |  |  | CAFAYATE_Attuatori danneggiati durante trasporto | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
351 | link 351 | / | 2019 | 03-mar | c | EMEA | Camponeschi | 2019-03-20 |  |  | 12081 |  | NCS | CSI |  |  | manca NC ufficiale_EUDER_Italzinc_Main beam con difetto di zincatura |  | 2019-04-09 |  |  |  |  | Fornitore |  |  | Azione di correzione indicata nella NC
352 | link 352 | / | 2019 | 04-apr | c | LATAM | Rodrigues | 2019-04-12 |  |  | 12154 |  | NCS | NUTFIL |  | SPACER - DIMENSIONS ERRORS | CAFAYATE_Nutfil_non conforming spacers Bottom M14 | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
353 | link 353 | / | 2019 | 04-apr | c | LATAM | Sanchez Perez | 2019-04-30 |  |  | 12155 |  | NCS | MD LOGISTICA |  |  | MD LOGISTICA_SKC danneggiata durante trasporto | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
354 | link 354 | / | 2019 | 05-may | c | LATAM | Camponeschi | 2019-05-02 |  |  | 12011 |  | NCS | NUOVACEVA |  | ANEMOMETERS | S&W_faliures of anemometers | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
355 | link 355 | / | 2019 | 05-may | c | EMEA | Mandrini | 2019-05-16 |  |  | 12123 |  | NCS | CSI |  |  | Caderousse_CSI_Main Beam with excess of Zinc (subsupp Italzinc) | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
356 | link 356 | / | 2019 | 05-may | c | EMEA | Mandrini | 2019-05-16 |  |  | 12122 |  | NCS | CSI |  |  | Bollene_CSI_Module Support with uncoated area from Zinc (subsupp Galvantubi) | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
357 | link 357 | / | 2019 | 05-may | c | EMEA | Mandrini | 2019-05-17 |  |  | 12081 |  | NCC | BULFER |  | HARDW - RIVETS | NCR EGP 71_Euder_Bulfer_rivets_mandrel too hard |  | 2019-05-27 |  |  |  |  | Fornitore |  |  | Azione di correzione indicata nella NC
358 | link 358 | / | 2019 | 05-may | c | EMEA | Mandrini | 2019-05-17 |  |  | 12081 |  | NCC | BULFER |  | HARDW - EXCESSIVE TORQUE | NCR EGP 71_Euder_Bulfer_M8 DIN 980_out of dimensional tolerance |  | 2019-05-27 |  |  |  |  | Fornitore |  |  | Azione di correzione indicata nella NC
359 | link 359 | / | 2019 | 05-may | c | EMEA | Camponeschi | 2019-05-20 |  |  | 12157 |  | NCS |  | R&D |  | Internal_Central Saddle vers. Universal_mounting interference | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
360 | link 360 | / | 2019 | 05-may | c | LATAM | Rodrigues | 2019-05-20 |  |  | 12154 |  | NCS | SIDERSA |  |  | Cafayate_Sidersa_Main Beam with welding defects | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
361 | link 361 | / | 2019 | 05-may | c | LATAM | Rodrigues | 2019-05-20 |  |  | 12155 |  | NCS | SIDERSA |  |  | Ullum_Sidersa_Main Beam with welding defects | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
362 | link 362 | / | 2019 | 05-may | c | EMEA | Mandrini | 2019-05-09 |  |  | 12081 |  | NCC | CSI |  | HARDW - POS HDG - ZINC DROP | NCR EGP 71_Euder_CSI_Module Supports with the holes closed by zinc |  | 2019-08-02 |  |  |  |  | Fornitore |  |  | Azione di correzione indicata nella NC
363 | link 363 | / | 2019 | 05-may | c | EMEA | Camponeschi | 2019-05-09 |  |  | 12081 |  | NCC |  | QUALITY | HSE | NCR EGP 70_Euder_Convert_HSE plan not in compliance |  | 2019-05-28 |  |  |  |  | Fornitore |  |  | Azione di correzione indicata nella NC
364 | link 364 | / | 2019 | 05-may | c | LATAM | Rodrigues | 2019-05-20 |  |  | 12155 |  | NCS | SIDERSA |  |  | Ullum_Sidersa_Main Beam with galvanizing defects | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
365 | link 365 | / | 2019 | 11-nov | c |  | Mandrini | 2018-11-12 |  |  | 11898 |  | NCC |  | SITE SERVICES | INSTALLATION | Zambia_NCR 2 EGP_Pile installation out of tolerance in respect to heights specified in Convert specificatioons and method statement | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
366 | link 366 | / | 2019 | 12-dec | c |  | Mandrini | 2018-12-27 |  |  | 11898 |  | NCC |  | SITE SERVICES | INSTALLATION | Zambia_NCR 7 EGP_Poor finish of work | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
367 | link 367 | / | 2019 | 12-dec | c |  | Mandrini | 2018-12-31 |  |  | 11898 |  | NCC |  | SITE SERVICES | INSTALLATION | Zambia_NCR 8 EGP_Curing of the concrete cubes | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
368 | link 368 | / | 2019 | 05-may | c | EMEA | Mandrini | 2019-05-07 |  |  | 12081 |  | NCC |  | QUALITY | HARDW - POS HDG - ZINC DROP | NCR EGP 68_Euder Se detecta material de Convert con defectos de fabricazion en galvanizato |  | 2019-05-28 |  |  |  |  | Fornitore |  |  | Azione di correzione indicata nella NC
369 | link 369 | / | 2019 | 06-june | c | LATAM | Camponeschi | 2019-06-06 |  |  | 12011 |  | NCC |  | ENGINEERING | TRJ - PRODCUT NO COMPLIANT | S&W_shadows in the modules | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
370 | link 370 | / | 2019 | 06-june | c | EMEA | Mandrini | 2019-06-17 |  |  | 12123 |  | NCS | WUERTH |  |  | Caderousse_Wurth_Serrated lock washer, externally serrated | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
371 | link 371 | / | 2019 | 06-june | c | EMEA | Camponeschi | 2019-06-18 |  |  | 12081 |  | NCS | CSI |  | MR - DIMENSIONS ERRORS | Euder_CSI_Long plate |  | 2019-06-21 |  |  |  |  | Fornitore |  |  | Azione di correzione indicata nella NC
372 | link 372 | / | 2019 | 06-june | c | EMEA | Mandrini | 2019-06-18 |  |  | 12081 |  | NCS | CSI |  |  | Euder_CSI_Support A B & C |  | 2019-08-02 |  |  |  |  | - |  |  | No CA is foreseen
373 | link 373 | / | 2019 | 06-june | c | EMEA | Mandrini | 2019-06-18 |  |  | 12081 |  | NCS | CSI |  |  | Euder_CSI_Support A B & C rounded |  | 2019-08-02 |  |  |  |  | Fornitore |  |  | Azione di correzione indicata nella NC
374 | link 374 | / | 2019 | 06-june | c | EMEA | Mandrini | 2019-06-27 |  |  | 12081 |  | NCC | BULFER |  |  | Euder_NC98EGPvsConvert_Euder_Bulfer_threaded rods-flanged nuts |  | 2019-08-01 |  |  |  |  | Fornitore |  |  | Azione di correzione indicata nella NC
375 | link 375 | / | 2019 | 07-july | c | EMEA | Camponeschi | 2019-07-08 |  |  | 11948 |  | NCS | BULFER |  |  | Magazzino_Bulfer_thin nut DIN 439 with lower hardness | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
376 | link 376 | / | 2019 | 07-july | c | EMEA | Mandrini | 2019-07-11 |  |  | 12157 |  | NCS | CSI |  |  | Manni_CSI_Support C (Campo Pino) | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
377 | link 377 | / | 2019 | CANC | canc | LATAM | Camponeschi | 2019-07-22 |  |  | 12155 |  | NCC |  |  | CANC | ULLUM_NCR004ELMYAvsConvert_Linear Actuator moved by wind | [9 empty] | Azione di correzione indicata nella NC
378 | link 378 | / | 2019 | 08-aug | c | LATAM | Camponeschi | 2019-08-27 |  |  | 12154 |  | NCC | NUTFIL |  |  | CAFAYATE_NCR007ELMYAvsCONVERT_oxidized bolts | [6 empty] | Fornitore |  |  | Azione di correzione indicata nella NC
379 | link 379 | / | 2019 | 09-sep | c | LATAM | Camponeschi | 2019-09-02 |  |  | 12011 |  | NCC | SIDERSA |  |  | S&W_EG_NC-66S&WvsCONVERT_Main Beam oxidezed | [9 empty] | Azione di correzione indicata nella NC
380 | link 380 | / | 2019 | 09-sep | c | LATAM | Rodrigues | 2019-09-06 |  |  | n.a. |  | NCS | VENTANA |  |  | VENTANA_13 damaged Main Beam during handling | [6 empty] | Supplier |  |  | Azione di correzione indicata nella NC
381 | link 381 | / | 2019 | 09-sep | c | LATAM | Rodrigues | 2019-09-10 |  |  | 12154 |  | NCC | SIDERSA |  |  | Cafayate_Sidersa_Main Beam transversal weld | [6 empty] | Sidersa |  |  | Implementation of automatic system for separating defective tubes in line
382 | link 382 | / | 2019 | 09-sep | c | EMEA | Mandrini | 2019-09-18 |  |  | 12234 |  | NCS | OSIM PLOCCO |  | KIT - DIMENSIONS ERRORS | Canino_OSIM Plocco_incorrect sizes |  | 2019-09-23 |  |  |  |  | - |  |  | No CA is foreseen
383 | link 383 | / | 2019 | 08-aug | c | LATAM | Mandrini | 2019-08-28 |  |  | 12154 |  | NCS | FEMAX |  | DIODE - DEFECTIVE PIECES | Cafayate_Femax_defective diode |  | 2019-10-23 |  |  |  |  | - |  |  | No CA is foreseen
384 | link 384 | / | 2019 | 10-oct | c | EMEA | Camponeschi | 2019-10-30 |  |  | 12237 |  | NCS | GEOINTEC |  | INSTALLATION | CamposdelSol_Geointec_PoT Activities
385 | link 385 | / | 2019 | 10-oct | c | EMEA | Mandrini | 2019-10-25 |  |  | 12081 |  | NCS | SIR |  | ACTUATOR - MAGNETIZED | EUDER_SIR_Linear Actuators defective | [6 empty] | SIR
386 | link 386 | / | 2019 | 11-nov | c | EMEA | Mandrini | 2019-11-05 |  |  | 12208 |  | NCS | SIR |  | ACTUATOR - MAGNETIZED | ENI_SIR_Linear Actuators defective
387 | link 387 | / | 2019 | CANC | canc |  | Mandrini | 2019-11-20 |  |  | 12154 |  | NCS |  |  | CANC | Cafayate_Wurth Elettronik_Terminal bloc contacts | [6 empty] | Wurth Elettronik
388 | link 388 | / | 2020 | 01-jan | c | LATAM | Rodrigues | 2020-01-13 |  |  | GD |  | NCS | VENTANA |  |  | CdB-GD_Main beam 7450mm_damaged during handling as a bundle fell to the ground | [6 empty] | Ventana |  | handling/packaging
389 | link 389 | / | 2020 | 01-jan | c | LATAM | Rodrigues | 2020-01-20 |  |  | 12153 |  | NCS | USIMINAS |  |  | CdB-Usiminas_Left and Right head pile_wrong pcs due to wrong blank | [6 empty] | Usiminas |  | blank | Azione di indicata nella non conformità
390 | link 390 | / | 2020 | 02-feb | c | LATAM | Rodrigues | 2020-02-18 |  |  | 12153/016 |  | NCS | USIMINAS |  | KIT - DIMENSIONS ERRORS | CdB-Usiminas_Central Saddle_internal dimension less than the tolerance not allowing the assembly | [8 empty] | bending
391 | link 391 | / | 2020 | 02-feb | c | LATAM | Rodrigues | 2020-02-27 |  |  | 12153 |  | NCS | REX |  | HARDW - POS HDG - ZINC DROP | CdB_REX_Parafuso ZF - M8x40_zinc drops | [8 empty] | zinc drops
392 | link 392 | / | 2020 | 03-mar | c | LATAM | Rodrigues | 2020-03-04 |  |  | 12153 |  | NCS | REX |  |  | CDB-QUAL- Parafusaria M16x100 ZF_excessive outside diameter | [8 empty] | diameter
393 | link 393 | / | 2020 | 03-mar | c | EMEA | Mandrini | 2020-03-30 |  |  | 12294 | Danville | NCS | CSI |  |  | Danville Valmont_CSI_Main Beam bundles moved in container during transport | [8 empty] | packaging - container
394 | link 394 | / | 2020 | 03-mar | c | EMEA | Mandrini | 2020-03-31 |  |  | 12294 | Danville | NCS | BULFER |  |  | Danville Valmont_BULFER_interferenza vite da 14mm_excessive outside diameter | [8 empty] | diameter
395 | link 395 | / | 2020 | 03-mar | c | EMEA | Mandrini | 2020-03-31 |  |  | 12234 | Canino | NCS | SIR |  | ACTUATOR - MAGNETIZED | Canino_SIR_Linear Actuators defective_lose position and noisy | [8 empty] | sensor - encoder - mechanical
396 | link 396 | / | 2020 | 05-may | c | EMEA | Mandrini | 2020-05-19 |  |  | 12234 | Campos del Sol | NCS | DEMIN |  |  | Campos del Sol_DeMin_KIT galvanizing defects | [8 empty] | zinc uncoated - zinc holes closed
397 | link 397 | / | 2020 | 05-may | c | EMEA | Mandrini | 2020-05-19 |  |  | 12237 | Campos del Sol | NCS | CSI |  |  | Cmpos del Sol_CSI_module supports_error in loading |  | 2020-05-20 | [6 empty] | packaging - container
398 | link 398 | / | 2020 | 05-may | c | EMEA | Sanchez Perez | 2020-05-19 |  |  | 12237 | Campos del Sol | NCS | ERL |  |  | Campo del Sol_ERL_Omega Pile_galvanizing defects |  | 2020-05-29
399 | link 399 | / | 2020 | 05-may | c | EMEA | Mandrini | 2020-05-25 |  |  | 12237 | Campos del Sol | NCS | CSI |  |  | CDS_CSI_Long Plate |  | 2020-06-26 |  |  |  |  | CSI
400 | link 400 | / | 2020 | CANC | canc |  | Mandrini |  |  |  | 12237 |  | NCS |  |  | CANC
401 | link 401 | / | 2020 | 09-sep | c | EMEA | Mandrini | 2020-09-07 |  |  | 12237 | Campos del Sol | NCS | CSI |  |  | CDS_CSI_Omega Pile welded
402 | link 402 | / | 2020 | 07-july | c | LATAM | Rodrigues | 2020-07-15 |  |  | GD-021 |  | NCS | USIMINAS |  |  | CDB_USI_Module Supports defects
403 | link 403 | / | 2020 | 07-july | c | LATAM | Rodrigues | 2020-07-15 |  |  | GD-021 |  | NCS | USIMINAS |  |  | CDB_USI_Module Supports defects
404 | link 404 | / | 2020 | 08-aug | c | LATAM | Rodrigues | 2020-08-11 |  |  | GD-Origem Energia |  | NCS | STARFIX |  |  | CDB_Starfix_fasteners non conformity
405 | link 405 | / | 2020 | CANC | canc | [10 empty] | CANC
406 | link 406 | / | 2020 | CANC | canc | [10 empty] | CANC
407 | link 407 | / | 2020 | 10-oct | c | LATAM | Rodrigues | 2020-10-06 |  |  | 12261 |  | NCS | USIMINAS |  |  | CDB_SGIII_Omega Pile defects on packaging
408 | link 408 | / | 2020 | CANC | canc | [10 empty] | CANC
409 | link 409 | / | 2020 | 09-sep | c | EMEA | Mandrini | 2020-09-28 |  |  | 12352 | Manni Energy | NCS | CSI |  |  | MANNI ENERGY_CSI_Module Supports defects on galvanization
410 | link 410 | / | 2020 | 10-oct | c | EMEA | Camponeschi | 2020-10-06 |  |  | 12237 | Campos del Sol | NCS | FATOR |  | SPRING WASHERS | Campos del Sol_FATOR_Washers M14 & M16 non conformity | Replaced electrolytic galvanized washers with hot galvanized washers. total quantity replaced: M16 - 836.040 pcs; M14 - 69.670 pcs. | 2021-02-19 |  |  | 320 | 333224.16
411 | link 411 | / | 2020 | 10-oct | c | LATAM | Conrado | 2020-10-07 |  |  | 12261 |  | NCS | USIMINAS |  |  | CDB_SGIII_USI_one tie with defects
412 | link 412 | / | 2020 | 10-oct | c | EMEA | Camponeschi | 2020-10-08 |  |  | 12352 - 12367 | Manni & Kiefer | NCS | FATOR |  |  | MANNI & KIEFER_FATOR_fasteners with defects | to replace the components with defects |  |  |  | 40
413 | link 413 | / | 2020 | 10-cot | c | EMEA | Mandrini | 2020-10-13 |  |  | 12367 | Kiefer | NCS | I&S |  |  | KIEFER_I&S_Cantilever with defects | accept as is | 2020-10-13 |  |  | 8 | 0
414 | link 414 | / | 2020 | 10-oct | c | LATAM | Ramon Conrado | 2020-10-14 |  |  | 12261 |  | NCS | USIMINAS |  |  | CdB_SGIII_USI_packaging defects
415 | link 415 | / | 2020 | CANC | canc | [10 empty] | CANC
416 | link 416 | / | 2020 | 10-oct | c | EMEA | Mandrini | 2020-10-20 |  |  | 12237 | Campos del Sol | NCS | I&S |  | KIT - DIMENSIONS ERRORS | Campos del Sol_I&S_Central Saddle defects | Prepared a tool from I&S to rework Central Saddles. Sent the tool to Campo del Sol, the defective parts will be reworked by Enoch. | 2022-02-17 |  |  | 80
417 | link 417 | / | 2020 | 10-oct | c | EMEA | Mandrini | 2020-10-22 |  |  | 12298 | Magazzino | NCS | ACS |  | SKC - DEFECTS | Magazzino_ACS_SKC with defects |  |  |  |  | 16
418 | link 418 | / | 2020 | 10-oct | c | LATAM | Rodrigues | 2020-10-29 |  |  | 12261 |  | NCS | MAXDEL |  | SPRING WASHERS | CdB_SGIII_Maxdel_M14 and M16 washers |  | 2020-11-04
419 | link 419 | / | 2020 | 11-nov | c | EMEA | Sanchez Perez | 2020-11-13 |  |  | 12123 | Caderousse | NCS | CSI |  |  | CADEROUSSE_CSI_Main Beam with defects |  |  |  |  | 16
420 | link 420 | / | 2020 | 12-dec | c | EMEA | Camponeschi | 2020-12-15 |  |  | 12011-12123-12041-12042-12043-11980-11981 | Various Project | NCS | NUOVACEVA |  | ANEMOMETERS | VARIOUS PJ_NUOVACEVA_Anemometer defect | accepted as is by Convert R&D. Dept. |  |  |  | 40 | 0
421 | link 421 | / | 2020 | 12-dec | c | EMEA | Camponeschi | 2020-12-29 |  |  | 12375 | Nardo | NCS | BULFER |  | HARDW - EXCESSIVE TORQUE | NARDO_Bulfer_M10x40 with defects | replacement of the non-compliant batch MVITE00464 n° lotto 23016, quantità 7.800pcs |  |  |  | 24
422 | link 422 | / | 2020 | 12-dec | c | EMEA | Camponeschi | 2020-12-29 |  |  | 12417 | Regran | NCS | BULFER |  | HARDW - EXCESSIVE TORQUE | REGRAN_Bulfer_Bolts M10 with defects |  |  |  |  | 24
423 | link 423 | / | 2021 | 01-jan | c | LATAM | Ramon Conrado | 2021-01-05 |  |  | 12261 |  | NCS | USIMINAS |  |  | CdB_SGIII_USI_Module Supports with defects |  | 2021-03-02
424 | link 424 | / | 2021 | 02-feb | c | LATAM | Ramon Conrado | 2021-02-08 |  |  | 12261 |  | NCS | USIMINAS |  |  | CdB_SGIII_USI_Module Supports with defects |  | 2021-05-31
425 | link 425 | / | 2021 | 02-feb | c | EMEA | Mandrini | 2021-02-04 |  |  | 12449 | Branch | NCS | CSI |  |  | Valmont_Branch_CSI_Omega Pile_slot hole with conform | accepted as is by Convert Eng. Dept. | 2021-02-04 |  |  | 8 | 0
426 | link 426 | / | 2021 | 02-feb | c | EMEA | Trancalini | 2021-02-12 |  |  | 12449 | Branch | NCS | I&S |  |  | Valmont_Branch_I&S_TIE_ some holes are blocked | reworked by I&S | 2021-02-16 |  |  | 8 | 0 | see NC 449
427 | link 427 | / | 2021 | 02-feb | c | EMEA | Trancalini | 2021-02-11 |  |  | 12449 | Branch | NCS | I&S |  |  | BRANCH_I&S_Central Saddle holes | accepted as is by Convert Eng. Dept. | 2021-02-12 |  |  | 8 | 0
428 | link 428 | / | 2021 | 03-mar | c | LATAM | Ramon Conrado | 2021-03-02 |  |  | 12261 |  | NCS | USIMINAS |  | MR - DIMENSIONS ERRORS | SGIII_USI_Module Support Type LS |  | 2021-05-26
429 | link 429 | / | 2021 | 03-mar | c | EMEA | Mandrini | 2021-03-19 |  |  | 12375 | Nardò | NFC | BULFER |  |  | NARDO_Bulfer_M16x160 with defects |  |  |  |  | 16
430 | link 430 | / | 2021 | 03-mar | c | LATAM | Ramon Conrado | 2021-03-30 |  |  | 12261 |  | NCS | USIMINAS |  |  | SGLIII-Soluções Usiminas_Embalagem
431 | link 431 | / | 2021 | 04-apr | c | NA | Massimo Mandrini | 2021-04-26 |  |  | 12344 | Valmont R&D | NCS | POWERNICE |  |  | VALMONT R&D-POWERNICE_head terminal unscrewed&oil leakage |  |  |  |  | 40
432 | link 432 | / | 2021 | 05-may | c | NA | Massimo Mandrini | 2021-05-10 |  |  | 12344 | Valmont R&D | NCS | POWERNICE |  | ACTUATOR - LOAD | Valmont R&D-POWERNICE_spherical joint load limit_rev01 | for 65kN actuator the sphercial joint component was replaced with a more performing one. | 2021-06-18 |  |  | 80
433 | link 433 | / | 2021 | 05-may | c | EMEA | Massimo Mandrini | 2021-05-21 |  |  | 12298 | Magazzino | NCS | COSTRUZIONI METALLICHE D’AMELIO |  | SPACER - DIMENSIONS ERRORS | D'AMELIO_inox spacers | on 27-05 a load test was carried out in Pomezia which allowed for the acceptance of the lot ‘as is’. | 2021-05-27 |  |  | 8
434 | link 434 | / | 2021 | 06-june | c | EMEA | Massimo Mandrini | 2021-06-08 |  | PO25571 | 12478 | Regran | NCS | BULFER |  | HARDW - EXCESSIVE TORQUE | REGRAN-BULFER_screw-lock nut M14 |  |  |  |  | 24
435 | link 435 | / | 2021 | 06-june | c | LATAM | Ramon Conrado | 2021-06-02 |  |  | 12261 |  | NCS | USIMINAS |  | MR - DIMENSIONS ERRORS | CdB_SGIII_USI_Module Support S errors
436 | link 436 | / | 2021 | 06-june | c | LATAM | Ramon Conrado | 2021-06-02 |  |  | 12261 |  | NCS | USIMINAS |  |  | CdB_SGIII_USI_Cantilever |  | 2021-07-06
437 | link 437 | / | 2021 | 06-june | C | EMEA | Massimo Mandrini | 2021-06-17 |  | PO25530 | 12478 | Regran | NCS | CSI |  | 1. MR - DIMENSIONS ERRORS 2. MR - POS-HDG 3. MR - DEFECTIVE PIECES | REGRAN-CSI_Module Supports |  |  |  |  | 24 |  | see NC 449
438 | link 438 | / | 2021 | 06-june | c | EMEA | Massimo Mandrini | 2021-06-17 |  | PO25538 | 12432 | Gualdo Tadino | NCS | CSI |  |  | GUALDO TADINO_CSI_Omega Pile | accepted as is by Convert Eng. Dept. | 2021-06-18 |  |  | 8 | 0
439 | link 439 | / | 2021 | 06-june | C | EMEA | Massimo Mandrini | 2021-06-17 |  | PO25600 | 12419 | Lula Bayware | NCS | CSI |  |  | LULA BAYWARE_CSI_Omega Pile | accepted as is by Convert Eng. Dept. | 2021-06-23 |  |  | 8 | 0
440 | link 440 | / | 2021 | 06-june | C | EMEA | Massimo Mandrini | 2021-06-23 |  | PO25621 | 12496 | Manni Civitavecchia | NCS | CSI |  |  | MANNI CIVITAVECCHIA_CSI_Omega Pile height | accepted as is by Convert Eng. Dept. | 2021-06-23 |  |  | 8 | 0
441 | link 441 | / | 2021 | 07-july | c | EMEA | Massimo Mandrini | 2021-07-02 |  | PO25621 | 12496 | Manni Civitavecchia | NCS | CSI |  |  | MANNI CIVITAVECCHIA_CSI_Module Supports packaging | re-packed by Convert in Pomezia | 2021-09-03 |  |  | 16 | ??? | see NC 451
442 | link 442 | / | 2021 | 07-july | c | EMEA | Massimo Mandrini | 2021-07-02 |  | PO25621, | 12496 | Manni Civitavecchia | NCS | CSI |  |  | MANNI CIVITAVECCHIA_CSI_Main Beam damaged | 11 pcs replaced by CSI. Defect pcs to be sent to CSI premises. Main Beam will remain on site. Close |  |  |  | 16
443 | link 443 | / | 2021 | 07-july | c | EMEA | Massimo Mandrini | 2021-07-05 |  | PO25593-25594-25595-25596 | CM12492-12493-12494-12495 | ACEA_Enertronica 1-2-3-4 | NCS | CSI |  |  | ACEA ENERTRONICA 1-2-3-4_DeMin_Tie & Saddles holes closed by zinc | reworked by DeMin on site. | 2021-09-09 |  |  |  |  | see NC 449
444 | link 444 | / | 2021 | 07-july | c | LATAM | Ramon Conrado | 2021-07-16 |  |  | 12261 | São Gonçalo | NCS | MAXDEL |  | SPRING WASHERS | SGIII_MAXDEL_hardware_spring washers broken
445 | link 445 | / | 2021 | 07-july | c | EMEA | Massimo Mandrini | 2021-07-13 |  |  | ??? | ??? | NCS | ERL |  |  | first article approval on 1P KIT components provided by supplier ERL. Sizes of holes of components KT30A3B920, KT3001B920, KT3201B920, KT3101B920 were found to be less than minimum tolerances. | new prototypes submitted for approval on 05/08/2021 | 2021-08-05 |  |  | 8 |  | see NC 449
446 | link 446 | / | 2021 | 09-sep | c | EMEA | Massimo Mandrini | 2021-09-21 |  |  | 12517 |  | NCS | CSI |  |  | Barrafranca_CSI_Omega Pile | accepted as is by Convert Eng. Dept. | 2021-09-21 |  |  | 8 | 0
447 | link 447 | / | 2021 | 09-sep | c | EMEA | Massimo Mandrini | 2021-09-21 |  |  | 12505 | Heliopolis | NCS | CSI |  |  | CM12505-Heliopolis Romania - packaging - articles KT1285D520 and KT1289D520 |  |  |  |  | 8 |  | see NC 451
448 | link 448 | / | 2021 | 09-sep | c | NA | Deruk | 2021-09-18 |  |  | 12499 | Brightwood | NCS | POWERNICE |  | ACTUATOR - WIRING | The wiring is not properly landed on the terminal strip | adding sleeves in cabling. Missing confirmation by R&D on sleeve proposed by Powernice | 2021-12-20 |  |  | 24 |  |  |  |  | adding sleeves in cabling. Missing confirmation by R&D on sleeve proposed by Powernice
449 | link 449 | / | 2021 | 09-sep | c | EMEA | Massimo Mandrini | 2021-09-10 |  |  | 12499 | Brightwood | NCS | DEMIN |  |  | holes occluded by zinc | to be reworked by Valmont team |  |  |  | 16 |  | Luca B. 2P Sara J. 1P | Flavio C. Ramon C. Stefano T. Egemen M. |  | Analyze possibility to increase holes of Head Pile: 8mm and 14mm: FC to open ECO. OPENED. Antonio to reply ECO Analyze where to design technical holes for galvanization process, could be ones of the component or one more. To analyze galvanizing process with suppliers to understand the most favorable area where to apply hooking hole. - 1P global product. No any opportunity to increase the holes. The component has specific holes to hook up the components. Executive drawings already updated, AC Resp. to check feedback. - 2P global product. No any opportunity to increase the holes. The component has specific holes to hook up the components. Executive drawings already updated, AC Resp. to check feedback.
450 | link 450 | / | 2021 | 10-oct | c | EMEA | Massimo Mandrini | 2021-10-13 |  |  | 12499 | Brightwood | NCS | DEMIN |  | KIT - HEAD PILE ASSEMBLY ERRORS | some of the bearing assembly bolts some are not screwed, nuts are loose and free to move. Others, are screwed to a torque higher than the limit set by the specification of 27Nm (± 10%). | to be reworked by Valmont team
451 | link 451 | / | 2021 | 10-oct | c | EMEA | Massimo Mandrini | 2021-10-07 |  |  | 12498 | ESPE - URAS | NCS | CSI |  |  | 1. Packages arrived with unfastened straps. 2. the upper pack collapsed on the lower ones, with possible damage to the material. 3. the discharge of the material could be dangerous for people The material has been accepted by Convert’s Client on site with reserve, any damaged components must therefore be replaced. | The material has been accepted by Convert’s Client on site with reserve, any damaged components must therefore be replaced. |  |  |  |  | 0 | Egemen M. Ramon Conrado Flavio C. | Daniele E. Stefano T. Jose A. |  | to standardize packaging with partner suppliers. Packaging has to be quality/cost optimized. Analyze if there is any difference in sea/land deliveries (i.e. how to load/unload, how to fix the units etc..). Analyze the feasibility of having a single Global solution. To highlight cost associated with the solution, for both, with a single global solution or production country optimized. To start with Standard components. Analyze the possibility of creating a package that allows the recovery of the same. Start by discussing it with BRA Team. Adolfo sharing best practices with Suppliers. General packaging requirements drafted. Specific packaging details for component to be drafted. Note: generated document Client side, highlighting the transloading process. To decide whether to make a single document (client + supplier) or two separate ones. The Team decided to have two reference documents, one client side and one supplier side: - client side - to merge informative note of Egemen with old Convert docuement, Egemen+Flavio; - supplier side - general requirements _ to be uploaded in sharepoint 'Flavio' ; to create specific annexes for components 'Flavio+Egemen+Ramon Conrado'
452 | link 452 | / | 2021 | 10-oct | c | EMEA | Massimo Mandrini | 2021-10-14 |  | PO25938 | 12512 | CIPRO | NCS | CSI |  |  | The KT1286D620 LS type supports has measures B and C not conforming to the drawing. The KT1289D620 Support type E has dimensions D and E not conforming to the drawing. The two components were made with revision designs DM 02, while the designs with revision DM03 had already been issued. |  | 2021-10-29
453 | link 453 | / | 2021 | 10-oct | c | EMEA | Massimo Mandrini | 2021-10-11 |  |  | 12505 e 12512 | Heliopolis & CIPRO | NCS | ITALWEBER ELETTRA |  | TRAFO - LABEL ERRORS | Upon receipt of the article KT08474304 (OTTC0801201255) at our warehouse we found that the labels applied outside and inside the transformer do not correspond to the certificates issued by Italweber. | R&D department considered not critical to link each pieces to the related test report by defining the correct serial number, as the test report were similar and the compents are made with the same raw material | 2021-10-11 |  |  |  | 0
454 | link 454 | / | 2021 | 10-oct | c | EMEA | Massimo Mandrini | 2021-10-13 |  |  | 12498 e 12487 | URAS e MONTECASSIANO | NCS | COSTRUZIONI METALLICHE D’AMELIO |  | SPACER - BURRS | Montecassiano and Uras projects, the M14x22 spacers were found with the presence of burrs which prevented assembly with M14 screw. The spacers were reworked on site by Convert's clients. | Reworked on site by Client | 2021-12-17
455 | link 455 | / | 2021 | 10-oct | c | LATAM | Ramon Conrado | 2021-10-08 |  |  | 12261 | São Gonçalo | tbd | SIR | tbd |  | SGIII_SIR_actuator broken | CONV BRA to deliver 3 sample to SIR CONV DO BRASIL delivered 5 sample to CONV ITA, CONV ITA delivered it to SIR. Actually under SIR analysis SIR replied that most of the failures were due to high pull force, so not depending on product. | 25/10/2021 04/05/2022 (received CITA) 10/06/2022 (deliv to SIR) 27/06/2022
456 | link 456 | / | 2021 | 10-oct | c | EMEA | Massimo Mandrini | 2021-10-13 |  | ???? | 12499 | Brightwood | NCS | BULFER |  |  | M8x40 and related nut M8 provided by supplier Bulfer trying to screw in the loose screws, it was noticed that the threads on the bolt stripping off while attempting to torque the nut to 27Nm. | to be reworked by Valmont Team, estimated time week 41/42
457 | link 457 | / | 2021 | 10-oct | c | EMEA | Massimo Mandrini | 2021-10-13 |  | PO26244 | 12451 | Magazzino | NCS | COSTRUZIONI METALLICHE D’AMELIO |  | SPACER - DIMENSIONS ERRORS | Checking the material received on 12/10/2021, of the order PO26244, the thickness of the spacers was lower than the one reported on drawing KT106302dm05 | accept as is. Close | 2021-10-13 |  |  |  | 0
458 | link 458 | / | 2021 | CANC | canc | EMEA | Massimo Mandrini | 2021-10-14 |  | ??? | ??? | ??? | NCS |  |  | CANC | on 14 October 2021 was highlighted that SIR delivered to Convert stock 95 SKC for the 100-M product, declared as defective.
459 | link 459 | / | 2021 | 10-oct | c | EMEA | Massimo Mandrini | 2021-10-19 |  |  | 12505 | Heliopolis | NCS | CSI |  |  | 1. Packages arrived with straps unfastened. 2. the upper pack collapsed on the lower ones, with possible damage to the material. 3. the bags are damaged and the components come out of the packaging The material has been accepted by Convert’s Client on site with reserve, any damaged components must therefore be replaced. | [6 empty] | see NC 451
460 | link 460 | / | 2021 | CANC | canc | EMEA | Massimo Mandrini | 2021-10-20 |  | ??? | ??? | ??? | NCS | I&S |  | CANC | Massimo mail sentence: "The drawing I got from Sharepoint has different tolerances 73.0 + 1.0 -0 from the one I&S has the revision is the same."
461 | link 461 | / | 2021 | 10-oct | c | EMEA | Massimo Mandrini | 2021-10-21 |  | PO25938 | 12512 | CIPRO | NCS | CSI |  |  | n° 1 of KT1280D620 Main beam T1 (6703) (2.5mm) and n° 2 of KT1297D620 Main beam T2 (6416) (2.5mm), components supplied by CSI supplier, arrived damaged on site | CSI will replace defected MBs | ETC first or second week of March 25/03/2022 closed
462 | link 462 | / | 2021 | 10-oct | c | EMEA | Massimo Mandrini | 2021-10-27 |  | PO25938 | 12512 | CIPRO | NCS | CSI |  |  | The bundles arrived opened and collapsed forcing Client to unload Omega Pile component individually by hand | none | 2021-11-03 |  |  |  |  | see NC 451
463 | link 463 | / | 2021 | CANC | canc | EMEA | Massimo Mandrini | 2021-11-09 |  | various | various | Various Project | NCI | TBD | TBD | CANC | Comparing Elisa's file with our drawings and our orders, actually held only for MAIN BEAM, it come out: our drawings by OBTON and UNDO are almost all in revision 1 while in Elisa's file I see revision 0; the code of MAIN BEAM KT1280D4DM00 of SANZARA is wrong the right one is KT1280F4DM01; the code of MAIN BEAM KT1281H4DM00 of MINERVINO2 is wrong the right one is KT1279H4DM01 as per order; our drawing KT1279H420 had wrong title block now it has been corrected | TBD
463 | link 463 | / | 2021 | 11-nov | c | EMEA | Massimo Mandrini | 2021-11-22 |  | PO25937 | 12505 | Heliopolis | NCS | CSI |  |  | Omega Pile component has buttonhole interaxis 151mm instead of 157mm. | Accepted as is by CONVERT ITALIA R&D Dept. |  |  |  |  | 0
464 | link 464 | / | 2021 | CANC | canc | EMEA | Massimo Mandrini | 2021-11-22 |  | PO25616 | 12528 | WHYSOL | NCS | DEMIN |  | CANC | Tie component has excess zinc which prevents assembly with Main Beam / Saddle / hardware assembly. | Possible treatment solution: immediate replacement of the M10x30 screw with M10x40, or, if available, the dispatch of replacement ties; for Quagliotto we supplied 2500 screws and 552 ties; other.
465 | link 465 | / | 2021 | 12-dec | c | EMEA | Massimo Mandrini | 2021-12-07 |  | PO26147 | 12505 | Heliopolis | NCS | CASTAGNOLI VITERIE |  |  | The assembled component broken during mounting with others Tracker components. The assembly was not properly carried out, the screw was not inserted perfectly into the blind nut during the first assembly phases, with fresh resin.
466 | link 466 | / | 2022 | 01-jan | c | EMEA | Massimo Mandrini | 2022-01-17 | Production | PO26171 | 12515 - 12521 | CUBICO | NCS | CSI |  | MR - DIMENSIONS ERRORS | The holes were not executed in the correct position | replaced by supplier | 2022-02-02
| link 467 | / | 2022 | CANC | canc | EMEA
468 | link 468 | / | 2022 | 02-feb | c | NA | Houyi | 2022-02-10 | On site | various | various | Various Project | NCS | POWERNICE |  | ACTUATOR - NO SELF-LOCKED | actuator move under a pulse force | R&D is developing a self locking system | Replaced by Convert
| link 469 | / | 2022 | CANC | canc
470 | link 470 | / | 2022 | 02-feb | c | EMEA | Flavio Camponeschi | 2022-02-18 | NC BY CLIENT | PO26183 | 12554 | Teatek | NCC | DEMIN |  | KIT - WELDING QUALITY | remarks by client on weldings and documentation. | Convert reply - the remarks does not represent a non conformity | 2022-03-04
471 | link 471 | / | 2022 | 02-feb | c | EMEA | Flavio Camponeschi | 2022-02-18 | NC BY CLIENT | PO26183 | 12554 | Teatek | NCC | DEMIN |  | DOCUMENTATION | remarks by client on weldings and documentation. | convert shared missing documents | 2022-03-04
472 | link 472 | / | 2022 | 03-mar | c | LATAM | Ramon Conrado | 2022-03-02 | On site | various | SGIII | São Gonçalo | NCS | ACS |  | SELF POWER - BURNED |  | Replaced by Convert
473 | link 473 | 410 | 2022 | 03-mar | c | EMEA | Flavio Camponeschi | 2022-03-11 | On site | various | 12237 | Campos del Sol | NCS | FATOR |  | SPRING WASHERS | About a percentage of 4% defects arised on M16 second batch. | Delivered a third batch of mechanical zinc washers: - M16, 30.000 pcs by air; - M16, 60.000 pcs by vessel. The third batch was produced by Castagnoli Viterie, below test herd on laboratory: SEE IN FOLDER Below example picture bending test held in Pomezia: SEE IN FOLDER THE NC WAS ESCALED TO LEGAL PART | ETA 12/08/2022 MAY 2022_CLOSED |  |  |  | 35067.86
474 | link 474 | / | 2022 | 04-apr | c | EMEA | Flavio Camponeschi | 2022-04-21 | On site | various | 12505 | Heliopolis | NCS | SIR |  | ACTUATOR - MAGNETIZED | magnetized actuators have been found in field which therefore lose reference of 'in' and consecutively 'out'. | taking advantage of spare parts containers shipment, metal clamps are also being sent. Two metal clamps per actuator will be assembled. Status today (23/06/2022): -TREMALZO, done - ROSSIORI, done | [5 empty] | Antonio T. | Flavio C. | under SIR investigation | until cause has been identified and an eventual alternative treatment established, metal clamps for single-phase and three-phase must always be provided.
| link 475 | / | 2022 | CANC | canc
476 | link 476 | / | 2022 | 05-may | c | EMEA | Flavio Camponeschi | 2022-05-19 | On site | PO26030 PO26327 | 12516; 12554; 12533 | TROIA/DELICETO; TEATEK; OBTON | NCS | DEMIN |  | KIT - WELDING QUALITY | Some units have undergone to spot welding stage, but not the next actual soldering stage. | TEATEK: delivered 10pcs under guarantee | TEATEK: 09/05/2022 |  |  |  | 4900
477 | link 477 | / | 2022 | 05-may | c | EMEA | Flavio Camponeschi | 2022-05-24 | Incoming goods | PO26924 PO27041 PO26843 | 12237; various | Campos del Sol; Solenova; Cipro | NCS | CASTAGNOLI VITERIE |  | SPRING WASHERS | Mechanical zinc detaches in form of flakes by testing the spring washers in the functional bend test. 8 D PROCESS AND INFO IN FOLDER | Accepted as is by CONVERT ITALIA R&D Dept. the evidence shows that after the assembly on the prototype, normal use of the product, the detachments are not present. They therefore only occur during the bend test (not normal use of the product). | 2022-05-24 |  |  |  |  | Antonio T. | Flavio C. | UNDER CONVERT/CASTAGNOLI ANALYSIS: CONVERT claims cause is due to a non-performing mechanical galvanizing process (i.e. process temperature, duration, etc.). CASTAGNOLI declares it represents normal behavior of mechanical galvanizing process. CONVERT shows result of test held on the same washer supplied by another supplier (Wuerth), the result highlight a better adhesion in this case. CASTAGNOLI requires sample washers and certificates. CASTAGNOLI shared Growermetal (mechanical zinc supplier): IN FOLDER | CASTAGNOLI proposed: -TS85 - Mechanical white zinc plating 15-20 my + TNT15 having a higher red corrosion resistance performance (> 500h red corrosion) with lower surface treatment thickness and fewer adhesion problems. -TS35 - Delta Protekt KL100 + VH302GZ 7-12 my which should have a red rust resistance performance of about 1000 hours in salt spray. Actually under CONVERT R&D Dept. analysis CONVERT R&D Dept. declared mechanical zinc coating adequate
478 | link 478 | / | 2022 | 05-may | c | EMEA | Flavio Camponeschi | 2022-05-24 | On site | open order | 12505 | Heliopolis | NCS | SIR |  | BEARING - ACTUATOR - UNSCREW | Upper bearing unscrews from the actuator. Possible cause, insufficient resin. | Replaced by new actuators sent to Heliopolis Porject | ANDREA DEVE REPLICARE |  |  |  | ANDREA DEVE REPLICARE
479 | link 479 | / | 2022 | 05-may | c | EMEA | Juan Sebastian Sanchez Perez | 2022-05-27 | Production |  | 12515 | Manduria | NCS | CSI |  | P - DIMENSIONS ERRORS | 10pcs of Omega Pile were non-compliant products. Incorrect machine setup, or production waste delivered by mistake. | Reject. Replaced by Supplier | 2022-06-30 |  |  |  | 587.8
480 | link 480 | / | 2022 | 05-may | c | EMEA | Flavio Camponeschi | 2022-05-23 | On site | 26981 | 12586 | SOLENOVA | NCC | ERL |  | KIT - DIMENSIONS ERRORS | CLIENT noted some details understanding them as non conformities. CONVERT reply that most of them are not non conformities, only for one note a functional test were performed to deem the component accepted as is. CLIENT noted some details understanding them as non conformities. CONVERT reply that most of them are not non conformities, only for one note a functional test were performed to deem the component accepted as is. | Accepted as is | 2022-06-01 |  |  |  | 0
481 | link 481 | / | 2022 | 06-june | c | EMEA | Juan Sebastian Sanchez Perez | 2022-06-06 | Production | PO270003 | 12586 | SOLENOVA | NCC | CSI |  | P - DIMENSIONS ERRORS | Componente Internal drive post KT1631K520: Il fornitore afferma di aver eseguito un stampo di foratura errato a 60mm e non a 65mm come indicato nel disegno -Il fornitore ha eseguito un processo di perforazione errato nella produzione. | Accepted as is | 2022-06-06 |  |  |  | 0
482 | link 482 | / | 2022 | 06-june | c | EMEA | Juan Sebastian Sanchez Perez | 2022-06-14 | Production | PO270003 | 12586 | SOLENOVA | NCC | CSI |  | MR - DIMENSIONS ERRORS | Il fornitore richiede una revisione su un problema di produzione che incide dimensionalmente sulle alette a 45° del Module Support S_ KT1285k520 Il disegno indica 11mm (+0,5 -0,5) e i componenti misurano fino a 6 mm in più. -Il fornitore informa che, Il +6 mm su cadauna aletta è dovuto ad un errore di sviluppo (lamiera sovrabbondante) | Accepted as is | 2022-06-14 |  |  |  | 0
483 | link 483 | / | 2022 | 06-june | c | EMEA | Juan Sebastian Sanchez Perez | 2022-06-20 | Production | PO26936 | 12237 | Campos del Sol | NCP | CSI |  | MR - DIMENSIONS ERRORS | Supplier CSI carried out first supply of CDS with bending angle of 90 ° as requested by executive drawing, subsequently CSI carried out second supply with bending angle of 45 °, in the same way of the ongoing projects were being carried out. Furthermore, the length of the wing was also greater. | Accepted as is by CONVERT Engineering Dept. | 2022-06-20
484 | link 484 | / | 2022 | 06-june | c | EMEA | Flavio Camponeschi | 2022-06-22 | On site | PO25711 | 12505 | Heliopolis | NCI |  | R&D | SMALL BOARD - DEFECTS | On Tremalzo cluster 10 pcs of small board, out of 346 pcs, present defects. | 80 pcs more as spare has been sent. firmware modification to limit absorption | 2022-05-06 | firmware modification to limit absorption will be executed in Project Solenova too.
485 | link 485 | / | 2022 | 07-july | c | EMEA | Flavio Camponeschi | 2022-06-28 | Incoming goods | PO27222 |  | SOLENOVA - CIPRO - various | NCS | SIR |  | ACTUATOR - NEW SHAPE LID BASE ASSEMB | matching of the actuator cover into the base. It seems that the edge on the lid does not fit perfectly into the groove in the base. In detail 4pcs out of 5pcs were open and 1pc closed. The open part was always the front one, in direction of actuator rod. | Adjusted production shape
486 | link 486 | / | 2022 | 07-july | c | EMEA | Juan Sebastian Sanchez Perez | 2022-07-04 | Production | PO27197 | 12587 | CIPRO2 | NCS | ERL |  | KIT - DIMENSIONS ERRORS | Central Saddle KT1082k6dm00 has one dimension out of tolerance | reworked by ERL
| link 487 | / | 2022 | 07-july | canc | EMEA | Flavio Camponeschi | 2022-07-18 | [8 empty] | inappropriate or defective actuators gears material.
488 | link 488 | / | 2022 | 07-july | c | EMEA | Flavio Camponeschi | 2022-07-22 | Production | PO27135 | 12589 | REGRAN_PROGESS&BONDIFE’ | NCS | CSI |  | MR - DIMENSIONS ERRORS | deviation in thickness of raw material used for Cantilever component of Progress and Bondifè clusters, project Regran | raw material replaced with correct one | 2022-07-25
489 | link 489 | / | 2022 | 08-aug | c | EMEA | Benedetto Beltrame | 2022-08-31 | Production | PO26322 | 12627 | ASSEMINI I&II | NCS | ACS |  | SKC - DEFECTS | programming connector that does not allow correct insertion of the pin. The non-compliant quantity found was approximately 50% out of a total of 500 pieces analysed
490 | link 490 | / | 2022 | 09-sep | c | EMEA | Flavio Camponeschi | 2022-09-15 | On site | PO27090 | 12589 | CIPRO 2 | NCS | CSI |  | MR - MISSING HOLES | Module Support E KT1665K620 with the absence of a hole. In total the defective components are 33 on Kokkinotremithia cluster and 106 on Ioannis cluster. component was badly bent, this defect makes more difficult to insert the screw into the hole. | Both defects will be reworked by client
491 | link 491 | / | 2022 | 09-sep | c | EMEA | Flavio Camponeschi | 2022-09-28 | Incoming goods | PO27355 | various | Various Project | NCS | ERL |  | PACKAGING - LOGISTIC | On 26/09/2022 CONVERT received material from ERL of order PO27355 almost all the pallets/package were broken. Pallets were made in a way that differs from CONVERT specifications, we also highlight a pallet about 2m high which also involves safety problems. | reworked by Convert
492 | link 492 | / | 2022 | 10-oct | c | EMEA | Flavio Camponeschi | 2022-10-13 | Production | PO26839 | various | POMEZIA – GELA1 – ACEA5 | NCS | DEMIN |  | KIT - POS HDG - ZINC THICKNESS | non compliance regarding zinc thickness about components of 8mm steel thickness | accept as is | 2022-10-13
493 | link 493 | / | 2022 | 10-oct | c |  | Flavio Camponeschi | 2022-10-14 | Incoming goods | PO27559 | various | Various Project | NCS | L'ELETTRICA DI PAOLO E.M. |  | DB - WIRING | The Distribution Board is wired non-compliant | reworked by Convert | 2022-10-14
| link 494 | / | 2022 | 10-oct | canc
495 | link 495 | / | 2022 | 11-nov | c | EMEA | Flavio Camponeschi | 2022-11-29 | On site | PO27489 | 12627 | Assemini I&II | NCS | CSI |  | MR - POS HDG - HOLES GALVANIZING | Module Supports received on Assemini projects have hole where rivets are to be fitted closed by zinc. | reworked by Convert | on progress
496 | link 496 | / | 2022 | 12-dec | c | EMEA | Flavio Camponeschi | 2022-12-12 | On site | PO27355 | 12627 | Assemini I&II | NCS | ERL |  | KIT - HEAD PILE ASSEMBLY ERRORS | Different types of head pile press-formed plate were assembled. | different approches depending on site phases. | on progress
497 | link 497 | / | 2023 | 02-feb | c | EMEA | Flavio Camponeschi | 2023-02-09 | Incoming goods | PO28224 | various | Various Project | NCS | ITALWEBER ELETTRA |  | SELF POWER - PAINTING | Self Power with painting defects that involve protruding areas that could cause damage to other components | reworked by Convert | 2023-02-17
498 | link 498 | / | 2023 | 02-feb | c | EMEA | Juan Sebastian Sanchez Perez | 2023-02-17 | Installation | PO27837 | 12627 | Assemini I_Bonomo | NCS | OPERE GEOTECNICHE |  | INSTALLATION | Pre-drilling activity for installation of the Omega Pile component was performed incorrectly. | to be reworked with new Omega Pile by supplier | 2023-04-28
| link 499 | / | 2023 | 02-feb | canc | EMEA | Roberto Biagi | 2023-02-21 | [8 empty] | Incorrect panel assembly
500 | link 500 | / | 2023 | 03-mar | c | EMEA | Flavio Camponeschi | 2023-03-20 | On site |  | 12633 | Obton - Rondissone | NCS | CASTAGNOLI VITERIE |  | HARDW - DAMAGED | Supply of M16 nut with notches | to be replaced by supplier
501 | link 501 | / | 2023 | 05-may | c | EMEA | Flavio Camponeschi | 2023-05-04 | On site | PO28715 | 12717 | AG SOLAR | NCS | CSI |  | MB - PRE HDG | Torque Tube - lack of galvanizing adhesion | to be replaced by supplier
502 | link 502 | / | 2023 | 04-apr | c | EMEA | Flavio Camponeschi | 2023-04-05 | On site |  | 12633 | Buia & Collepasso | NCS | CASTAGNOLI VITERIE |  | HARDW - POS HDG - DIMENSIONS ERROR | Some nuts do not match perfectly with the threaded rod, are too oversized. | Same lot of nuts received by client was tested in Pomezia premises. No main problem araised. Collepasso site, client bought nuts himself. Certification to be received. Plescioi, Roberta will ask client to send back some nuts and threaded rods to be tested.
503 | link 503 | / | 2023 | 05-may | c | EMEA | Flavio Camponeschi | 2023-05-12 | On site | PO28715 | 12682 | Gropella | NCS | CASTAGNOLI VITERIE |  | HARDW - POS HDG - DIMENSIONS ERROR | M16 nuts during assembly the threads broken | to be replaced by supplier. Replaced on 16/6/2023
504 | link 504 | / | 2023 | 05-may | c | EMEA | Flavio Camponeschi | 2023-05-15 | On site | PO??? | 12599 | Trino | NCS | CASTAGNOLI VITERIE |  | HARDW - ERROR IN TYPE OF PROD. DELIVERY | M20 washers were supplied instead of M16 | Replace washers that have not yet been assembled, then remove from site the incorrect ones. Monitor washers already assembled to see the behavior, Padovani in next inspection on site will check one tracker already in motion. Padovani checked the proper assembly of external washers. Replaced the ones still not assembled. | 2023-06-23
505 | link 505 | / | 2023 | 06-june | c | EMEA | Roberto Biagi | 2023-06-09 | Installation | PO??? | 12694 | UT3 | NCS | GENERALI COSTRUZIONI |  | INSTALLATION | In the area identified in layout as ZONE 2, an incorrect Omega Pile installation were identified. It can generate interference between solar panels during rotation. Convert staff will identify the number of Omega Pile affected for each row. | Currently NC tratment is summarized as follows: 1) Check Omega Pile alignment and relative driving heights; 2) In case of activity 1 result is negative, disassembly of the previously assembled superstructure 3) Ramming of Omega Pile up to mitigate the slope of the structure; 4) Filing and re-zinc finishing of the omega pile section; 5) Assembly of the structure. | 2023-10-13
506 | link 506 | / | 2023 | 06-june | c | EMEA | Flavio Camponeschi | 2023-06-20 | Incoming goods | PO28912 | various | Various Project | NCS | SIR |  | ACTUATOR - LABEL | 300pcs 45Kn actuator, KT10160108 P/N 6814620, order PO28912 received from supplier SIR. In detail, the component code shown on the actuator body is incorrect | SIR will supply 300 labels to Convert for replacement. SIR will add visual inspection on ATC | 2023-06-30
507 | link 507 | / | 2023 | 06-june | c | EMEA | Flavio Camponeschi | 2023-06-28 | On site | various | various | Various Project | NCS | ACS |  | SKC - DEFECTS | 1. OTTANA (NU): 1 SKC out of 7 has 1 motor command channel does not work; 2. SAN CRISTOFORO (FG): one of the SKC displayed IN and OUT simultaneously on all 10 channels. 3. FERRANTE (FG): system with 7 SKCs of which 2 SKCs do not light up even if the 230Vac is regular and the fuses are OK (to be replaced) and 1 SKC has a faulty channel, so it does not control the relative motor. | reworked by Convert | 2023-06-30
508 | link 508 | / | 2023 | 07-july | c | EMEA | Flavio Camponeschi | 2023-07-13 | On site | various | various | Various Project | NCS | STAR ELECTRIC |  | SKC - DEFECTS | Two non-conformities are highlighted: the first concerns the inversion of the Slave/SKC cables; the second one, to improve cabling by always ensuring that the copper is gripped. | reworked by Convert | 2023-07-13
509 | link 509 | / | 2023 | 07-july | c | EMEA | Flavio Camponeschi | 2023-07-13 | On site | PO??? | 12689 | Pedagaggi | NCS | CASTAGNOLI VITERIE |  | HARDW - POS HDG - DIMENSIONS ERROR | M16 defective, the threads give out during assembly. Estimated quantity of the defective pieces is 15200pcs. | to be replaced by Castagnoli Viterie
510 | link 510 | / | 2023 | 07-july | c | EMEA | Flavio Camponeschi | 2023-07-14 | On site | PO28178 | 12599 | Trino | NCS | CSI |  | MR - DIMENSIONS ERRORS | Module Support E bended at 17mm instead of 18mm. The percentage of defectives at the moment is 20/25%. | 17mm square washers will be produced to allow assembly.
| link 511 | / | 2023 | 06-giu | canc | EMEA | Juan Sebastian Sanchez Perez | 2023-06-23 | [8 empty] | PROF. OMEGA 15 X70 X35 ZIN S420GD +Z450 S=3 x690 MODULE RAIL TYPE P INT KT1282C520 6500 pz, adhesion problem, zinc wires cut during the bending phase​
512 | link 512 | / | 2023 | 09-sep | c | EMEA | Flavio Camponeschi | 2023-09-08 | On site | PO28178 | 12599 | Trino | NCS | CSI |  | MR - POS HDG - VARIOUS DEFECTS | The anomalies found on the total Trino supply can be summarized as follows: - P-P2 and P/P2Ext support are the most critical ones, approximately 80% of the supply. - S support approximately 10/20% - Long plate approximately 20% | reworked by client | tbd
| link 513 |  | 2023 |  | canc
514 | link 514 | / | 2023 | 10-oct | c | EMEA | Flavio Camponeschi | 2023-10-03 | Production | PO29615 | 12724 | Atri + Mottalciata | NCS | CARMET |  | MR - POS HDG - HOLES GALVANIZING | The module support components produced by the supplier CARMET have holes closed by zinc. | reworked by client | tbd
515 | link 515 | / | 2023 | 12-dec | a | EMEA | Flavio Camponeschi | 2023-12-06 | Production | various | various | Various Project | NCS | SIR |  | ACTUATOR - LOAD | The actuator of 45kN and 80kN do not reach the declared load | tbd | tbd
| link 516 |  | 2023 |  | canc
517 | link 517 | / | 2023 | 12-dec | c | EMEA | Flavio Camponeschi | 2023-12-12 | Production | PO29951 | 12652 | Cancello Arnone | NCS | CSI |  | P - DIMENSIONS ERRORS | the distance of the buttonhole from the end of the omega pile is non-compliant and presents a high variability. | Accepted as is | tbd
518 | link 518 | / | 2023 | 12-dec | c | EMEA | Flavio Camponeschi | 2023-12-15 | On site | PO29865 | 12670 | DELOS_FOSSANO, POGGIARDO, RIDULFO, TUTTISANTI | NCS | CSI |  | MR - POS HDG - HOLES GALVANIZING | Module support holes closed by zinc | reworked by client | tbd
519 | link 519 | / | 2023 | 12-dec | c | EMEA | Flavio Camponeschi | 2023-12-15 | On site | various | various | Various Project | NCS | SIR |  | PACKAGING - LOGISTIC | Missing plastic cover inside carton boxes | SIR has to restart inserting plastic cover inside carton boxes | tbd
520 | link 520 | / | 2023 | 06-giu | c | EMEA | Flavio Camponeschi | 2023-06-12 | On site |  | 12672 | Sonnedix Cluster _ PONTINIA 1 | NCS | CSI |  | MR - PRE HDG -CORROSION | the 1400 mm rails sent to Pontinia 1 has rust evidence at the base/top of the omega. | first apply a rust inhibitor such as Ferox, and then zinc spray (suggested under Faren F93 98% pure) | tbd
| link 521 |  | 2023 |  | canc
522 | link 522 | / | 2024 | 01-gen | c | EMEA | Flavio Camponeschi | 2024-01-25 | On site | PO28195 | 12635 | Piani della Marina | NCS | CASTAGNOLI VITERIE |  | HARDW - WASHER - GEOMET - GLUED | FLAT WASHER M.6 6.5X14X1.5 are "glued" following the Geomet 321B coating process. Currently the defect rate is 100pcs every 3,000 pcs. | to be replaced by Castagnoli Viterie | tbd
523 | link 523 | / | 2024 | 01-gen | c | EMEA | Flavio Camponeschi | 2024-01-25 | Incoming goods | PO29952 | various | Various Project | NCS | CASTAGNOLI VITERIE |  | HARDW - WASHER - GEOMET - GLUED | FLAT WASHER M16 17X34X3, our item MVITE00947, delivered with DDT number 276046. In detail they are “glued” following the hot-dip galvanizing coating process. Furthermore, incorrect items were found in boxes | to be replaced by Castagnoli Viterie | tbd
524 | link 524 | / | 2024 | 01-gen | c | EMEA | Juan Sebastian Sanchez Perez | 2024-01-30 | On site |  | 12533 | Barrafranca (White Truffle1) | NCS | SIR |  | BEARING - ACTUATOR - UNSCREW | An actuator produced by the supplier SIR the upper joint unscrewed, causing the tracker to move freely. | to be replaced on site | tbd
525 | link 525 | / | 2024 | 01-gen | c | EMEA | Juan Sebastian Sanchez Perez | 2024-01-31 | On site |  | 12681 | Cascina Sant'Angelo | NCS | DEMIN |  | KIT - DIMENSIONS ERRORS | 30 pcs defective components of the double saddle which compromise the alignment during assembly. | to be replaced by Demin | tbd
| link 526 | / | 2024 | 02-feb | canc | EMEA | Flavio Camponeschi | [9 empty] | Sir attuatore non autobloccante
527 | link 527 | / | 2024 | 02-feb | a | EMEA | Flavio Camponeschi | 2024-02-21 | On site | tbd | 12496 | Manni Civitavecchia | NCS | CHIAVETTE UNIFICATE |  | BEARING - ACTUATOR - CORROSION | MANNI CIVITAVECCHIA approximately 50% of the actuator joints are oxidized as shown in the photos below approximately 2 years after installation. | investigating new materials bearing for both, head pile and actuator bearing | tbd
528 | link 528 | / | 2024 | 02-feb | a | EMEA | Flavio Camponeschi | 2024-02-22 | On site | tbd | 12496 | Manni Civitavecchia | NCS | CHIAVETTE UNIFICATE |  | BEARING - HEAD PILE BEARING - CORROSION | In MANNI CIVITAVECCHIA project, some units of the M16 bearing product, made by the supplier Chiavette Unificate, are oxidized after approximately 2 years from installation. | investigating new materials bearing for both, head pile and actuator bearing | tbd
529 | link 529 | / | 2024 | 02-feb | c | EMEA | Flavio Camponeschi | 2024-02-21 | Production | tbd | 12635 | Piani della Marina | NCS | DEMIN |  | P - DIMENSIONS ERRORS | In TRINO project were found Omega Pile, 7003767 (EX KT1631C520), produced by supplier DEMIN with different fin lengths compared to the executive drawing | accepted as is | 2024-02-23
| link 530 | / | 2024 |  | canc
531 | link 531 | / | 2024 | 03-mar | p | EMEA | Flavio Camponeschi | 2024-03-05 | Malpractice | tbd | 12635 | Piani della Marina | MP | CLIENT |  | INSTALLATION | Root cause analysis highlighted that the way in which this result can be achieved is by acting on the cross screw mounted axially on drive shaft using reduced power screwdrivers. Wrong practice performed by the customer. | damaged actuators to be replaced | tbd
532 | link 532 | / | 2024 | 03-mar | c | EMEA | Flavio Camponeschi | 2024-03-07 | Malpractice | tbd | 12784 | Larino | MP | CLIENT |  | INSTALLATION | Root cause analysis shown that concerns a little galvanizing line and not the welding. The detachment of the galvanization is caused by an assembly torque applied by the customer higher than that foreseen in the installation manual. | accepted as is | tbd
|  |  | 2024 |  | canc
534 | link 534 | / | 2024 | 03-mar | a | EMEA | Flavio Camponeschi | 2024-03-21 | On site |  | 12635 | Piani della Marina | NCS | SIR |  | BEARING - ACTUATOR - CORROSION | Actuator bearing supplied by SIR result as corrosed | investigating new materials bearing for both, head pile and actuator bearing | tbd
535 | link 535 | / | 2024 | 03-mar | a | EMEA | Flavio Camponeschi | 2024-03-21 | On site |  | 12670 | Ortigia Power | NCS | SIR |  | BEARING - ACTUATOR - CORROSION | Actuator bearing supplied by SIR result as corrosed | investigating new materials bearing for both, head pile and actuator bearing | tbd
536 | link 536 | / | 2024 | 03-mar | c | EMEA | Flavio Camponeschi | 2024-03-19 | On site | tbd | 12635 | Piani della Marina | NCS | CASTAGNOLI VITERIE |  | HARDW - WASHER - POS HDG - GLUED | PIANI DELLA MARINA project, 10x17 rectangular washers were found glued. The estimated amount is 20%. | to be replaced | tbd
| link 537 | / | 2024 |  | canc
538 | / | / | 2024 | 05-may | c | EMEA | Flavio Camponeschi | 2024-05-15 | Production | various | various | various | NCS | MARCEGAGLIA |  | DOCUMENTATION | Marcegaglia has to update Attestato di qualifica including S420GD. See treatment progress. | Attestato di qualifica to be updated including S420GD. Marcegaglia replaced that Consiglio Superiore dei Lavori Pubblici refused proposal to include S420GD. | end of 2024. Marcegaglia replaced that Consiglio Superiore dei Lavori Pubblici refused proposal to include S420GD.
539 | / | / | 2024 | 05-may | c | EMEA | Gabriele Arena | 2024-05-08 | Production |  | 12809 | JUWI POMEZIA | NCS | CSI |  | P - DIMENSIONS ERRORS | CSI produced Posts with wrong buttonhole dimension | to be reworked by CSI
540 | / | / | 2024 | 05-may | c | EMEA | Flavio Camponeschi | 2024-05-20 | On site |  | 12670 | De Marinis 2 | NCS | CSI |  | MR - DIMENSIONS ERRORS | CSI produced Module Rails with undersized square holes | Reworked on site by Client
541 | / | / | 2024 | 05-may | c | EMEA | Juan Sebastian Sanchez Perez | 2024-05-21 | On site |  | 12809 | JUWI POMEZIA | NCS | CSI |  | P - DIMENSIONS ERRORS | CSI delivered six wrong bundles on site. | Replaced by CSI
542 | / | / | 2024 | 05-may | c | EMEA | Juan Sebastian Sanchez Perez | 2024-05-23 | Production |  | 12748 | SANTA CROCE CAMERINA | NCS | CSI |  | MR - PACKAGING MIXING PRODUCTS | CSI delivered different module rails in the same pallet. | Replaced by CSI
543 | / | / | 2024 | 07-jul | c | EMEA | Flavio Camponeschi | 2024-06-24 | Incoming goods | various | various | various | NCS | CASTAGNOLI VITERIE |  | DOCUMENTATION | CASTAGNOLI VITERIE share documentation later than projects needs | CASTAGNOLI VITERIE has to improve the process i.e. Adding resources
544 | / | / | 2024 | 07-jul | c | EMEA | Gabriele Arena | 2024-07-16 | Production |  | 12822 | SANTO STEFANO | NCS | CSI |  | MR - DIMENSIONS ERRORS | CSI produced Cantilever component with wronged holes dimension | accepted as is
545 | / | / | 2024 | 07-jul | c | EMEA | Gabriele Arena | 2024-07-23 | Production |  | 12672, 12746 | CARENTINO, VERNA e NARO 1&2 | NCS | CSI |  | MR - DIMENSIONS ERRORS | CSI produced module rails for cantilever with wrong dimensions | accepted as is
546 | / | / | 2024 | 07-jul | c | EMEA | Gabriele Arena | 2024-07-23 | Production |  | 12672, 12746, 12629 | CARENTINO, VERNA, NARO 1&2 e PALUMBO | NCS | CSI |  | MR - PRE HDG - ZINC DAMAGED BY BENDING | CSI produced for these projects module rail for cantilever and cantilever rail with zinc defects | accepted as is
547 | / | / | 2024 | 07-jul | c | EMEA | Flavio Camponeschi | 2024-08-05 | Production |  | various | various | NCI | INTERNAL - R&D | R&D | ACTUATOR - NEW SHAPE GEARBOX ASSEMB | Actuator designed with new shape in lower area of gearbox can't be assembled due to interference | Use the same assembling kit of upper area to lower area.
548 | / | / | 2024 | 09-sep | c | EMEA | Gabriele Arena | 2024-09-05 | Production |  | various | MARRAFFA REVAMPING, PASTORE FRANCESCO, CAROSINO, PASTORE GIUSEPPE, PIGNATARO 2, PIRE REVAMPING, STOMEI REVAMPING, ASCIA REVAMPING, SAN GIORGIO, VIBO BALENTIA, CURBICI e BONDENO | NCS | DEMIN |  | KIT - POS HDG - ZINC THICKNESS | Demin produced kit components of 8mm with low zinc accordingly to ISO 1461 | Reworked by Demin
549 | / | / | 2024 | 09-sep | c | EMEA | Flavio Camponeschi | 2024-09-11 | Incoming goods |  | various | various | NCS | CASTAGNOLI VITERIE |  | HARDW - POS HDG - DIMENSIONS ERROR | Castagnoli Viterie produced M16x110 that can't fit with bearing due to excessive diameter size | Replaced by Castognoli Viterie
550 | / | / | 2024 | 10-oct | c | EMEA | Flavio Camponeschi | 2024-10-10 | On site |  | 12599; 12635 | TRINO, PIANI DELLA MARINA | NCS | ITALWEBER ELETTRA |  | TRAFO | Italweber produced components with loose electrical clamps | Reworked by Client
551 | / | / | 2024 | 10-oct | c | EMEA | Flavio Camponeschi | 2024-10-28 | Incoming goods |  | various | various | NCS | CASTAGNOLI VITERIE |  | HARDW - POS HDG - DIMENSIONS ERROR | Castagnoli Viteria produced M16x110 that can't fit with bearing due to excessive diameter size | Replaced by Castognoli Viterie
| / | / | 2024 |  | canc
553 | / | / | 2024 | 11-nov | c | EMEA | Juan Sebastian Sanchez Perez | 2024-11-19 | On site |  | 12743 | Sonnedix Cluster - Vada | NCS | DEMIN |  | KIT - WELDING QUALITY | Demin produced kit components with defects on weld | Replaced by Demin
554 | / | / | 2024 | 12-dec | c | EMEA | Gabriele Arena | 2024-12-03 | Incoming goods |  | various | various | NCS | CASTAGNOLI VITERIE |  | HARDW - POS HDG - DIMENSIONS ERROR | Castagnoli Viterie produced M14x100 that can't fit with bearing due to excessive diameter size | Replaced by Castognoli Viterie
555 | / | / | 2024 | 12-dec | c | EMEA | Gabriele Arena | 2024-12-03 | Incoming goods |  | various | various | NCS | SIR |  | ACTUATOR - PACKAGING | Thermal sealing phase of the internal bags performed imperfectly, some points are open and/or open easily. | Reworked by Convert
556 | / | / | 2024 | 12-dec | p | EMEA | Gabriele Arena | 2024-12-20 | On site |  | 12910 | Maresca Grammichele | NCS | CSI |  | MR - POS HDG - VARIOUS DEFECTS | Some areas of 7007254 “MODULE RAIL MIDDLE 44X2 790MM S355 HDG90” and 7007256 “MODULE RAIL END 19X50X2.25 790MM S420HDGl” are uncoated of zinc | Reworked by Convert
557 | / | / | 2024 | 12-dec | p | EMEA | Flavio Camponeschi | 2024-12-19 | NC BY CLIENT |  | 12905 | Nepi e Panevino | NCS | CSI |  | MR - POS HDG - VARIOUS DEFECTS | Omega Pile and Module Supports components with uncoated zinc areas. | reworked by Convert
558 | / | / | 2025 | 02-feb | p | EMEA | Gabriele Arena | 2025-02-07 | On site |  | 12910 | Maresca Grammichele | NCS | DEMIN |  | KIT - POS HDG - ZINC THICKNESS | components 7007210 “LEFT PRESS PLATE 8MM 355MPA 1P V2.1 90UM” and 7007211 “RIGHT PRESS PLATE DRIVE 8MM 355MPA 90UM” with holes closed by galvanizing process | Reworked by Convert
| / | / | 2025 | 01-jan | canc | EMEA | Flavio Camponeschi | 2025-02-24 | [8 empty] | SCREW M16X110 CL.8.8 HDG DIN 933 with a lower breaking load than that foreseen by the standard, but in reality it is compliant as it is an undersized screw.
560 | / | / | 2025 | 02-feb | c | EMEA | Federico Rossi | 2025-02-20 | Malpractice |  | 12910 | Maresca Grammichele | MP | CLIENT |  | INSTALLATION | GR1 a hole was drilled on the main beam codes 7007473/7007474/7007475/7007476 for the installation of an equipotential cable using a self-drilling screw. | Reworked by Client
561 | / | / | 2025 | 02-feb | c | EMEA | Federico Rossi | 2025-02-20 | Malpractice |  | 12910 | Maresca Grammichele | MP | CLIENT |  | HARDW - EXCESSIVE TORQUE | the tracker structures of sectors A and B of the MARESCA GRAMMICHELE project, a non-conformity was highlighted on the tightening torques of the M14 actuators (coupling 7001721 “NUT M14 CL. 8DIN 934 HDG” / 7004168 “SCREW M14X100 CL. 8.8DIN931 HDG NO STEM”). The detected values ​​fall between 70 and 90Nm for 100% of the analyzed samples, against the 50±20% Nm prescribed. the problem is extended to field D, but that the screw threads do not appear damaged. | Reworked by Supplier of Client
562 | / | / | 2025 | 02-feb | c | EMEA | Flavio Camponeschi | 2025-03-03 | Malpractice |  | 12753 | Montenero | MP | CLIENT |  |  | si evidenzia che durante le verifiche in campo su progetto Montenero 1, all’interno di un quadro SCADA, è stata riscontrata la fuoriuscita di acido dalle batterie | Reworked by Client
563 | / | / | 2025 | 29-apr | p | EMEA | Juan Sebastian Sanchez Perez | 2025-04-29 | On site |  | 12796 | NOTO | NCS | FAPI -CSI |  | KIT - WELDING QUALITY | si evidenzia che durante le verifiche in campo su progetto NOTO, abbiamo verificato che la segnalazione di una possibile cricca nella saldatura del componente KIT_ Double Saddle è stata confermata. È stata esclusa la possibilità di un difetto di zincatura o di un difetto superficiale passando un disco di tela abrasiva sulla zona, scoprendo così che la cricca prosegue internamente. | REWORK BY SUPPLIER
564 | / | / | 2025 | 05-mag | c | EMEA | Juan Sebastian Sanchez Perez | 2025-05-05 | Production |  | 12926 | JESI | NCS | FAPI -CSI |  | P - DIMENSIONS ERRORS | 232 pali L4 LATERAL POST, 155X110X50X4.5MM, 4200MM, S420MC, HDG_100 con l’asola più piccola del minimo indicato nel disegno | REWORK BY SUPPLIER
SIR reply